## Tasks
UID | ID | WBS | Outline Level | Name | Start | Finish | Duration | % Complete | Actual Start | Actual Finish | Baseline Start | Baseline Finish | Milestone | Summary | Critical | Constraint Type | Constraint Date | Predecessors | Successors | Resource Names | Notes
0 | 0 | 0 | 0 | schedule for VTP VOLARE Site 27-12-25- Tower T3 Client schedule-R2-14-01-2026 | 2025-10-18T08:00 | 2027-12-10T20:00 | 750.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2673 | 1 | 1 | 1 | VTP VOLARE, HINJEWADI PHASE - 1, PUNE. | 2025-10-18T08:00 | 2027-12-10T20:00 | 750.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
749 | 2 | 1.1 | 2 | RESIDENTIAL TOWER T-1 & NTA AREA | 2025-10-18T08:00 | 2027-12-10T20:00 | 750.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2717 | 3 | 1.1.1 | 3 | Project Planning | 2025-10-18T08:00 | 2025-11-20T20:00 | 30.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2718 | 4 | 1.1.1.1 | 4 | Letter of Acceptance | 2025-10-18T08:00 | 2025-10-18T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | START_NO_EARLIER_THAN | 2025-10-18T08:00 |  | 5SS, 7SS, 6SS
2719 | 5 | 1.1.1.2 | 4 | Mobilization Period | 2025-10-18T08:00 | 2025-11-20T20:00 | 30.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 4SS
2720 | 6 | 1.1.1.3 | 4 | Excavation Completion & Handing Over of Site | 2025-10-18T08:00 | 2025-10-18T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 4SS | 12FS, 430FS
3369 | 7 | 1.1.1.4 | 4 | GFC Drawing Receipt | 2025-10-18T08:00 | 2025-10-18T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 4SS | 8SS+15.0d, 12SS, 16FS, 52FS, 189FS, 430FS, 434FS
3372 | 8 | 1.1.1.5 | 4 | Steel Receipt | 2025-11-06T08:00 | 2025-11-10T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 7SS+15.0d | 16FS, 52FS, 189FS, 434FS
3374 | 9 | 1.1.2 | 3 | Tower 1 Schedule - for Tower | 2025-10-19T08:00 | 2027-11-19T20:00 | 728.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2721 | 10 | 1.1.2.1 | 4 | Foundation | 2025-10-19T08:00 | 2025-12-02T20:00 | 41.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2722 | 11 | 1.1.2.1.1 | 5 | Pour 1- SW6 to SW45 - 23 nos | 2025-10-19T08:00 | 2025-12-02T20:00 | 41.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2723 | 12 | 1.1.2.1.1.1 | 6 | Dressing | 2025-10-19T08:00 | 2025-10-24T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 6FS, 7SS | 13FS, 24SS+2.0d, 36SS+4.0d
2724 | 13 | 1.1.2.1.1.2 | 6 | PCC | 2025-10-25T08:00 | 2025-10-26T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 12FS | 14SS+5.0d
2726 | 14 | 1.1.2.1.1.3 | 6 | Waterproofing Work - Client scope | 2025-10-30T08:00 | 2025-11-03T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 13SS+5.0d | 16SS+3.0d
2727 | 15 | 1.1.2.1.1.4 | 6 | Raft - Pour 1 | 2025-11-11T08:00 | 2025-11-30T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2728 | 16 | 1.1.2.1.1.4.1 | 7 | Raft RF (Incl Footing, SW, RW & Tie Beam) | 2025-11-11T08:00 | 2025-11-25T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 14SS+3.0d, 7FS, 8FS | 17SS+8.0d
2729 | 17 | 1.1.2.1.1.4.2 | 7 | Shuttering | 2025-11-19T08:00 | 2025-11-27T20:00 | 9.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 16SS+8.0d | 18FS
2730 | 18 | 1.1.2.1.1.4.3 | 7 | Checking | 2025-11-28T08:00 | 2025-11-28T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 17FS | 19FS
2731 | 19 | 1.1.2.1.1.4.4 | 7 | Raft Concrete | 2025-11-29T08:00 | 2025-11-30T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 18FS | 21FS
2732 | 20 | 1.1.2.1.1.5 | 6 | Footing abover Raft - Pour 1 | 2025-12-01T08:00 | 2025-12-02T20:00 | 2.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2733 | 21 | 1.1.2.1.1.5.1 | 7 | Shuttering for Footing | 2025-12-01T08:00 | 2025-12-01T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 19FS | 22FS
2734 | 22 | 1.1.2.1.1.5.2 | 7 | Footing Concrete | 2025-12-02T08:00 | 2025-12-02T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 21FS | 52FS
2735 | 23 | 1.1.2.1.2 | 5 | Pour 2 SW41 - C316 - 17 nos | 2025-10-25T08:00 | 2025-11-25T20:00 | 32.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2736 | 24 | 1.1.2.1.2.1 | 6 | Dressing | 2025-10-25T08:00 | 2025-10-26T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 12SS+2.0d | 25FS
2737 | 25 | 1.1.2.1.2.2 | 6 | PCC | 2025-10-27T08:00 | 2025-10-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 24FS | 26SS+5.0d
2739 | 26 | 1.1.2.1.2.3 | 6 | Waterproofing Work - Client scope | 2025-11-01T08:00 | 2025-11-05T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 25SS+5.0d | 28SS+3.0d
2740 | 27 | 1.1.2.1.2.4 | 6 | Raft - Pour 2 | 2025-11-04T08:00 | 2025-11-25T20:00 | 22.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2741 | 28 | 1.1.2.1.2.4.1 | 7 | Raft RF (Incl Footing, SW, RW & Tie Beam) | 2025-11-04T08:00 | 2025-11-18T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 26SS+3.0d | 29SS+8.0d
2742 | 29 | 1.1.2.1.2.4.2 | 7 | Shuttering | 2025-11-12T08:00 | 2025-11-20T20:00 | 9.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 28SS+8.0d | 30FS
2743 | 30 | 1.1.2.1.2.4.3 | 7 | Checking | 2025-11-21T08:00 | 2025-11-21T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 29FS | 31FS
2744 | 31 | 1.1.2.1.2.4.4 | 7 | Raft Concrete | 2025-11-22T08:00 | 2025-11-23T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 30FS | 33FS
2745 | 32 | 1.1.2.1.2.4.5 | 7 | Footing abover Raft - Pour 2 | 2025-11-24T08:00 | 2025-11-25T20:00 | 2.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2746 | 33 | 1.1.2.1.2.4.5.1 | 8 | Shuttering for Footing | 2025-11-24T08:00 | 2025-11-24T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 31FS | 34FS
2747 | 34 | 1.1.2.1.2.4.5.2 | 8 | Footing Concrete | 2025-11-25T08:00 | 2025-11-25T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 33FS | 63FS
2748 | 35 | 1.1.2.1.3 | 5 | Pour 3 C310 to C314 -20 NOS | 2025-10-27T08:00 | 2025-11-28T20:00 | 33.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2749 | 36 | 1.1.2.1.3.1 | 6 | Dressing | 2025-10-27T08:00 | 2025-10-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 12SS+4.0d | 37FS
2750 | 37 | 1.1.2.1.3.2 | 6 | PCC | 2025-10-29T08:00 | 2025-10-30T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 36FS | 38FS
3375 | 38 | 1.1.2.1.3.3 | 6 | Rock Anchoring 4 Nos - Client Scope | 2025-10-31T08:00 | 2025-11-04T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 37FS | 39SS+4.0d
2752 | 39 | 1.1.2.1.3.4 | 6 | Waterproofing Work - Client Scope | 2025-11-04T08:00 | 2025-11-08T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 38SS+4.0d | 41SS+3.0d
2753 | 40 | 1.1.2.1.3.5 | 6 | Raft - Pour 3 | 2025-11-07T08:00 | 2025-11-28T20:00 | 22.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2754 | 41 | 1.1.2.1.3.5.1 | 7 | Raft RF (Incl Footing, SW, RW & Tie Beam) | 2025-11-07T08:00 | 2025-11-21T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 39SS+3.0d | 42SS+8.0d
2755 | 42 | 1.1.2.1.3.5.2 | 7 | Shuttering | 2025-11-15T08:00 | 2025-11-23T20:00 | 9.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 41SS+8.0d | 43FS
2756 | 43 | 1.1.2.1.3.5.3 | 7 | Checking | 2025-11-24T08:00 | 2025-11-24T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 42FS | 44FS
2757 | 44 | 1.1.2.1.3.5.4 | 7 | Raft Concrete | 2025-11-25T08:00 | 2025-11-26T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 43FS | 46FS
2758 | 45 | 1.1.2.1.3.5.5 | 7 | Footing abover Raft - Pour 3 | 2025-11-27T08:00 | 2025-11-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2759 | 46 | 1.1.2.1.3.5.5.1 | 8 | Shuttering | 2025-11-27T08:00 | 2025-11-27T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 44FS | 47FS
2760 | 47 | 1.1.2.1.3.5.5.2 | 8 | Footing Concrete | 2025-11-28T08:00 | 2025-11-28T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 46FS | 74FS
2761 | 48 | 1.1.2.2 | 4 | Sub Structure - Conventional RCC Slabs | 2025-11-26T08:00 | 2026-05-13T20:00 | 162.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2762 | 49 | 1.1.2.2.1 | 5 | Basement 2 - (1st Slab) | 2025-11-26T08:00 | 2026-01-03T20:00 | 39.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2763 | 50 | 1.1.2.2.1.1 | 6 | Basement 2 - Pour 1 | 2025-12-03T08:00 | 2026-01-03T20:00 | 32.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2764 | 51 | 1.1.2.2.1.1.1 | 7 | Column & Shear Wall | 2025-12-03T08:00 | 2025-12-15T20:00 | 13.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2765 | 52 | 1.1.2.2.1.1.1.1 | 8 | Reinforcement | 2025-12-03T08:00 | 2025-12-10T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 22FS, 7FS, 8FS | 53SS+4.0d
2766 | 53 | 1.1.2.2.1.1.1.2 | 8 | Shuttering | 2025-12-07T08:00 | 2025-12-12T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 52SS+4.0d | 54FS
2767 | 54 | 1.1.2.2.1.1.1.3 | 8 | Checking | 2025-12-13T08:00 | 2025-12-13T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 53FS | 55FS
2768 | 55 | 1.1.2.2.1.1.1.4 | 8 | Column & Shear wall Concrete | 2025-12-14T08:00 | 2025-12-15T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 54FS | 57FS
2769 | 56 | 1.1.2.2.1.1.2 | 7 | B2 Slab - Pour 1 | 2025-12-16T08:00 | 2026-01-03T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2770 | 57 | 1.1.2.2.1.1.2.1 | 8 | Slab Shuttering | 2025-12-16T08:00 | 2025-12-30T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 55FS | 58SS+7.0d
2771 | 58 | 1.1.2.2.1.1.2.2 | 8 | Reinforcement | 2025-12-23T08:00 | 2026-01-01T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 57SS+7.0d | 59FS
2772 | 59 | 1.1.2.2.1.1.2.3 | 8 | Checking | 2026-01-02T08:00 | 2026-01-02T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 58FS | 60FS
2773 | 60 | 1.1.2.2.1.1.2.4 | 8 | Slab Casting | 2026-01-03T08:00 | 2026-01-03T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 59FS | 86FS
2774 | 61 | 1.1.2.2.1.2 | 6 | Basement 2 - Pour 2 | 2025-11-26T08:00 | 2025-12-27T20:00 | 32.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2775 | 62 | 1.1.2.2.1.2.1 | 7 | Column & Shear Wall | 2025-11-26T08:00 | 2025-12-08T20:00 | 13.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2776 | 63 | 1.1.2.2.1.2.1.1 | 8 | Reinforcement | 2025-11-26T08:00 | 2025-12-03T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 34FS | 64SS+4.0d
2777 | 64 | 1.1.2.2.1.2.1.2 | 8 | Shuttering | 2025-11-30T08:00 | 2025-12-05T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 63SS+4.0d | 65FS
2778 | 65 | 1.1.2.2.1.2.1.3 | 8 | Checking | 2025-12-06T08:00 | 2025-12-06T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 64FS | 66FS
2779 | 66 | 1.1.2.2.1.2.1.4 | 8 | Column & Shear wall Concrete | 2025-12-07T08:00 | 2025-12-08T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 65FS | 68FS
2780 | 67 | 1.1.2.2.1.2.2 | 7 | B2 Slab - Pour 2 | 2025-12-09T08:00 | 2025-12-27T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2781 | 68 | 1.1.2.2.1.2.2.1 | 8 | Slab Shuttering | 2025-12-09T08:00 | 2025-12-23T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 66FS | 69SS+7.0d
2782 | 69 | 1.1.2.2.1.2.2.2 | 8 | Reinforcement | 2025-12-16T08:00 | 2025-12-25T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 68SS+7.0d | 70FS
2783 | 70 | 1.1.2.2.1.2.2.3 | 8 | Checking | 2025-12-26T08:00 | 2025-12-26T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 69FS | 71FS
2784 | 71 | 1.1.2.2.1.2.2.4 | 8 | Slab Casting | 2025-12-27T08:00 | 2025-12-27T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 70FS | 97FS
2785 | 72 | 1.1.2.2.1.3 | 6 | Basement 2 - Pour 3 | 2025-11-29T08:00 | 2025-12-30T20:00 | 32.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2786 | 73 | 1.1.2.2.1.3.1 | 7 | Column & Shear Wall | 2025-11-29T08:00 | 2025-12-11T20:00 | 13.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2787 | 74 | 1.1.2.2.1.3.1.1 | 8 | Reinforcement | 2025-11-29T08:00 | 2025-12-06T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 47FS | 75SS+4.0d
2788 | 75 | 1.1.2.2.1.3.1.2 | 8 | Shuttering | 2025-12-03T08:00 | 2025-12-08T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 74SS+4.0d | 76FS
2789 | 76 | 1.1.2.2.1.3.1.3 | 8 | Checking | 2025-12-09T08:00 | 2025-12-09T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 75FS | 77FS
2790 | 77 | 1.1.2.2.1.3.1.4 | 8 | Column & Shear wall Concrete | 2025-12-10T08:00 | 2025-12-11T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 76FS | 79FS
2791 | 78 | 1.1.2.2.1.3.2 | 7 | B2 Slab - Pour 3 | 2025-12-12T08:00 | 2025-12-30T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2792 | 79 | 1.1.2.2.1.3.2.1 | 8 | Slab Shuttering | 2025-12-12T08:00 | 2025-12-26T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 77FS | 80SS+7.0d
2793 | 80 | 1.1.2.2.1.3.2.2 | 8 | Reinforcement | 2025-12-19T08:00 | 2025-12-28T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 79SS+7.0d | 81FS
2794 | 81 | 1.1.2.2.1.3.2.3 | 8 | Checking | 2025-12-29T08:00 | 2025-12-29T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 80FS | 82FS
2795 | 82 | 1.1.2.2.1.3.2.4 | 8 | Slab Casting | 2025-12-30T08:00 | 2025-12-30T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 81FS | 108FS
2796 | 83 | 1.1.2.2.2 | 5 | Basement 1 - (2nd Slab) | 2025-12-28T08:00 | 2026-02-04T20:00 | 38.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2797 | 84 | 1.1.2.2.2.1 | 6 | Basement 1 - Pour 1 | 2026-01-04T08:00 | 2026-02-04T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2798 | 85 | 1.1.2.2.2.1.1 | 7 | Column & Shear Wall | 2026-01-04T08:00 | 2026-01-15T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2799 | 86 | 1.1.2.2.2.1.1.1 | 8 | Reinforcement | 2026-01-04T08:00 | 2026-01-11T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 60FS | 87SS+3.0d
2800 | 87 | 1.1.2.2.2.1.1.2 | 8 | Shuttering | 2026-01-07T08:00 | 2026-01-12T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 86SS+3.0d | 88FS
2801 | 88 | 1.1.2.2.2.1.1.3 | 8 | Checking | 2026-01-13T08:00 | 2026-01-13T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 87FS | 89FS
2802 | 89 | 1.1.2.2.2.1.1.4 | 8 | Column & Shear wall Concrete | 2026-01-14T08:00 | 2026-01-15T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 88FS | 91FS
2803 | 90 | 1.1.2.2.2.1.2 | 7 | B1 Slab - Pour 1 | 2026-01-16T08:00 | 2026-02-04T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2804 | 91 | 1.1.2.2.2.1.2.1 | 8 | Slab Shuttering | 2026-01-16T08:00 | 2026-01-31T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 89FS | 92SS+7.0d
2805 | 92 | 1.1.2.2.2.1.2.2 | 8 | Reinforcement | 2026-01-23T08:00 | 2026-02-02T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 91SS+7.0d | 93FS
2806 | 93 | 1.1.2.2.2.1.2.3 | 8 | Checking | 2026-02-03T08:00 | 2026-02-03T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 92FS | 94FS
2807 | 94 | 1.1.2.2.2.1.2.4 | 8 | Slab Casting | 2026-02-04T08:00 | 2026-02-04T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 93FS | 120FS
2808 | 95 | 1.1.2.2.2.2 | 6 | Basement 1 - Pour 2 | 2025-12-28T08:00 | 2026-01-28T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2809 | 96 | 1.1.2.2.2.2.1 | 7 | Column & Shear Wall | 2025-12-28T08:00 | 2026-01-08T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2810 | 97 | 1.1.2.2.2.2.1.1 | 8 | Reinforcement | 2025-12-28T08:00 | 2026-01-04T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 71FS | 98SS+3.0d
2811 | 98 | 1.1.2.2.2.2.1.2 | 8 | Shuttering | 2025-12-31T08:00 | 2026-01-05T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 97SS+3.0d | 99FS
2812 | 99 | 1.1.2.2.2.2.1.3 | 8 | Checking | 2026-01-06T08:00 | 2026-01-06T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 98FS | 100FS
2813 | 100 | 1.1.2.2.2.2.1.4 | 8 | Column & Shear wall Concrete | 2026-01-07T08:00 | 2026-01-08T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 99FS | 102FS
2814 | 101 | 1.1.2.2.2.2.2 | 7 | B1 Slab - Pour 2 | 2026-01-09T08:00 | 2026-01-28T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2815 | 102 | 1.1.2.2.2.2.2.1 | 8 | Slab Shuttering | 2026-01-09T08:00 | 2026-01-23T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 100FS | 103SS+7.0d
2816 | 103 | 1.1.2.2.2.2.2.2 | 8 | Reinforcement | 2026-01-16T08:00 | 2026-01-25T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 102SS+7.0d | 104FS
2817 | 104 | 1.1.2.2.2.2.2.3 | 8 | Checking | 2026-01-27T08:00 | 2026-01-27T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 103FS | 105FS
2818 | 105 | 1.1.2.2.2.2.2.4 | 8 | Slab Casting | 2026-01-28T08:00 | 2026-01-28T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 104FS | 131FS
2819 | 106 | 1.1.2.2.2.3 | 6 | Basement 1 - Pour 3 | 2025-12-31T08:00 | 2026-01-31T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2820 | 107 | 1.1.2.2.2.3.1 | 7 | Column & Shear Wall | 2025-12-31T08:00 | 2026-01-11T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2821 | 108 | 1.1.2.2.2.3.1.1 | 8 | Reinforcement | 2025-12-31T08:00 | 2026-01-07T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 82FS | 109SS+3.0d
2822 | 109 | 1.1.2.2.2.3.1.2 | 8 | Shuttering | 2026-01-03T08:00 | 2026-01-08T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 108SS+3.0d | 110FS
2823 | 110 | 1.1.2.2.2.3.1.3 | 8 | Checking | 2026-01-09T08:00 | 2026-01-09T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 109FS | 111FS
2824 | 111 | 1.1.2.2.2.3.1.4 | 8 | Column & Shear wall Concrete | 2026-01-10T08:00 | 2026-01-11T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 110FS | 113FS
2825 | 112 | 1.1.2.2.2.3.2 | 7 | B1 Slab - Pour 3 | 2026-01-12T08:00 | 2026-01-31T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2826 | 113 | 1.1.2.2.2.3.2.1 | 8 | Slab Shuttering | 2026-01-12T08:00 | 2026-01-27T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 111FS | 114SS+7.0d
2827 | 114 | 1.1.2.2.2.3.2.2 | 8 | Reinforcement | 2026-01-19T08:00 | 2026-01-29T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 113SS+7.0d | 115FS
2828 | 115 | 1.1.2.2.2.3.2.3 | 8 | Checking | 2026-01-30T08:00 | 2026-01-30T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 114FS | 116FS
2829 | 116 | 1.1.2.2.2.3.2.4 | 8 | Slab Casting | 2026-01-31T08:00 | 2026-01-31T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 115FS | 142FS
2830 | 117 | 1.1.2.2.3 | 5 | Stilt Floor Level - (3rd Slab) | 2026-01-29T08:00 | 2026-03-10T20:00 | 38.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2831 | 118 | 1.1.2.2.3.1 | 6 | Stilt Floor - Pour 1 | 2026-02-05T08:00 | 2026-03-10T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2832 | 119 | 1.1.2.2.3.1.1 | 7 | Column & Shear Wall | 2026-02-05T08:00 | 2026-02-16T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2833 | 120 | 1.1.2.2.3.1.1.1 | 8 | Reinforcement | 2026-02-05T08:00 | 2026-02-12T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 94FS | 121SS+3.0d
2834 | 121 | 1.1.2.2.3.1.1.2 | 8 | Shuttering | 2026-02-08T08:00 | 2026-02-13T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 120SS+3.0d | 122FS
2835 | 122 | 1.1.2.2.3.1.1.3 | 8 | Checking | 2026-02-14T08:00 | 2026-02-14T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 121FS | 123FS
2836 | 123 | 1.1.2.2.3.1.1.4 | 8 | Column & Shear wall Concrete | 2026-02-15T08:00 | 2026-02-16T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 122FS | 125FS
2837 | 124 | 1.1.2.2.3.1.2 | 7 | Stilt Floor - Pour 1 | 2026-02-17T08:00 | 2026-03-10T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2838 | 125 | 1.1.2.2.3.1.2.1 | 8 | Slab Shuttering | 2026-02-17T08:00 | 2026-03-06T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 123FS | 126SS+7.0d
2839 | 126 | 1.1.2.2.3.1.2.2 | 8 | Reinforcement | 2026-02-24T08:00 | 2026-03-08T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 125SS+7.0d | 127FS
2840 | 127 | 1.1.2.2.3.1.2.3 | 8 | Checking | 2026-03-09T08:00 | 2026-03-09T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 126FS | 128FS
2841 | 128 | 1.1.2.2.3.1.2.4 | 8 | Slab Casting | 2026-03-10T08:00 | 2026-03-10T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 127FS | 154FS
2842 | 129 | 1.1.2.2.3.2 | 6 | Stilt Floor - Pour 2 | 2026-01-29T08:00 | 2026-02-28T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2843 | 130 | 1.1.2.2.3.2.1 | 7 | Column & Shear Wall | 2026-01-29T08:00 | 2026-02-09T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2844 | 131 | 1.1.2.2.3.2.1.1 | 8 | Reinforcement | 2026-01-29T08:00 | 2026-02-05T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 105FS | 132SS+3.0d
2845 | 132 | 1.1.2.2.3.2.1.2 | 8 | Shuttering | 2026-02-01T08:00 | 2026-02-06T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 131SS+3.0d | 133FS
2846 | 133 | 1.1.2.2.3.2.1.3 | 8 | Checking | 2026-02-07T08:00 | 2026-02-07T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 132FS | 134FS
2847 | 134 | 1.1.2.2.3.2.1.4 | 8 | Column & Shear wall Concrete | 2026-02-08T08:00 | 2026-02-09T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 133FS | 136FS
2848 | 135 | 1.1.2.2.3.2.2 | 7 | Stilt Floor - Pour 2 | 2026-02-10T08:00 | 2026-02-28T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2849 | 136 | 1.1.2.2.3.2.2.1 | 8 | Slab Shuttering | 2026-02-10T08:00 | 2026-02-24T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 134FS | 137SS+7.0d
2850 | 137 | 1.1.2.2.3.2.2.2 | 8 | Reinforcement | 2026-02-17T08:00 | 2026-02-26T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 136SS+7.0d | 138FS
2851 | 138 | 1.1.2.2.3.2.2.3 | 8 | Checking | 2026-02-27T08:00 | 2026-02-27T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 137FS | 139FS
2852 | 139 | 1.1.2.2.3.2.2.4 | 8 | Slab Casting | 2026-02-28T08:00 | 2026-02-28T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 138FS | 165FS
2853 | 140 | 1.1.2.2.3.3 | 6 | Stilt Floor - Pour 3 | 2026-02-01T08:00 | 2026-03-06T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2854 | 141 | 1.1.2.2.3.3.1 | 7 | Column & Shear Wall | 2026-02-01T08:00 | 2026-02-12T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2855 | 142 | 1.1.2.2.3.3.1.1 | 8 | Reinforcement | 2026-02-01T08:00 | 2026-02-08T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 116FS | 143SS+3.0d
2856 | 143 | 1.1.2.2.3.3.1.2 | 8 | Shuttering | 2026-02-04T08:00 | 2026-02-09T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 142SS+3.0d | 144FS
2857 | 144 | 1.1.2.2.3.3.1.3 | 8 | Checking | 2026-02-10T08:00 | 2026-02-10T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 143FS | 145FS
2858 | 145 | 1.1.2.2.3.3.1.4 | 8 | Column & Shear wall Concrete | 2026-02-11T08:00 | 2026-02-12T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 144FS | 147FS
2859 | 146 | 1.1.2.2.3.3.2 | 7 | Stilt Floor - Pour 3 | 2026-02-13T08:00 | 2026-03-06T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2860 | 147 | 1.1.2.2.3.3.2.1 | 8 | Slab Shuttering | 2026-02-13T08:00 | 2026-02-27T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 145FS | 148SS+7.0d
2861 | 148 | 1.1.2.2.3.3.2.2 | 8 | Reinforcement | 2026-02-20T08:00 | 2026-03-01T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 147SS+7.0d | 149FS
2862 | 149 | 1.1.2.2.3.3.2.3 | 8 | Checking | 2026-03-02T08:00 | 2026-03-02T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 148FS | 150FS
2863 | 150 | 1.1.2.2.3.3.2.4 | 8 | Slab Casting | 2026-03-06T08:00 | 2026-03-06T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 149FS | 176FS
2864 | 151 | 1.1.2.2.4 | 5 | 1st Floor Level - (4th Slab) | 2026-03-01T08:00 | 2026-05-13T20:00 | 68.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2865 | 152 | 1.1.2.2.4.1 | 6 | 1st Floor - Pour 1 | 2026-03-11T08:00 | 2026-04-12T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2866 | 153 | 1.1.2.2.4.1.1 | 7 | Column & Shear Wall | 2026-03-11T08:00 | 2026-03-24T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2867 | 154 | 1.1.2.2.4.1.1.1 | 8 | Reinforcement | 2026-03-11T08:00 | 2026-03-18T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 128FS | 155SS+3.0d
2868 | 155 | 1.1.2.2.4.1.1.2 | 8 | Shuttering | 2026-03-14T08:00 | 2026-03-19T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 154SS+3.0d | 156FS
2869 | 156 | 1.1.2.2.4.1.1.3 | 8 | Checking | 2026-03-20T08:00 | 2026-03-20T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 155FS | 157FS
2870 | 157 | 1.1.2.2.4.1.1.4 | 8 | Column & Shear wall Concrete | 2026-03-23T08:00 | 2026-03-24T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 156FS | 159FS
2871 | 158 | 1.1.2.2.4.1.2 | 7 | 1st Floor - Pour 1 | 2026-03-25T08:00 | 2026-04-12T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2872 | 159 | 1.1.2.2.4.1.2.1 | 8 | Slab Shuttering | 2026-03-25T08:00 | 2026-04-08T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 157FS | 160SS+7.0d
2873 | 160 | 1.1.2.2.4.1.2.2 | 8 | Reinforcement | 2026-04-01T08:00 | 2026-04-10T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 159SS+7.0d | 161FS
2874 | 161 | 1.1.2.2.4.1.2.3 | 8 | Checking | 2026-04-11T08:00 | 2026-04-11T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 160FS | 162FS
2875 | 162 | 1.1.2.2.4.1.2.4 | 8 | Slab Casting | 2026-04-12T08:00 | 2026-04-12T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 161FS | 185FS
2876 | 163 | 1.1.2.2.4.2 | 6 | 1st Floor - Pour 2 | 2026-03-01T08:00 | 2026-04-05T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2877 | 164 | 1.1.2.2.4.2.1 | 7 | Column & Shear Wall | 2026-03-01T08:00 | 2026-03-15T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2878 | 165 | 1.1.2.2.4.2.1.1 | 8 | Reinforcement | 2026-03-01T08:00 | 2026-03-11T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 139FS | 166SS+3.0d
2879 | 166 | 1.1.2.2.4.2.1.2 | 8 | Shuttering | 2026-03-07T08:00 | 2026-03-12T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 165SS+3.0d | 167FS
2880 | 167 | 1.1.2.2.4.2.1.3 | 8 | Checking | 2026-03-13T08:00 | 2026-03-13T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 166FS | 168FS
2881 | 168 | 1.1.2.2.4.2.1.4 | 8 | Column & Shear wall Concrete | 2026-03-14T08:00 | 2026-03-15T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 167FS | 170FS
2882 | 169 | 1.1.2.2.4.2.2 | 7 | 1st Floor - Pour 2 | 2026-03-16T08:00 | 2026-04-05T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2883 | 170 | 1.1.2.2.4.2.2.1 | 8 | Slab Shuttering | 2026-03-16T08:00 | 2026-04-01T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 168FS | 171SS+7.0d
2884 | 171 | 1.1.2.2.4.2.2.2 | 8 | Reinforcement | 2026-03-25T08:00 | 2026-04-03T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 170SS+7.0d | 172FS
2885 | 172 | 1.1.2.2.4.2.2.3 | 8 | Checking | 2026-04-04T08:00 | 2026-04-04T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 171FS | 173FS
2886 | 173 | 1.1.2.2.4.2.2.4 | 8 | Slab Casting | 2026-04-05T08:00 | 2026-04-05T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 172FS | 185FS
2887 | 174 | 1.1.2.2.4.3 | 6 | 1st Floor - Pour 3 | 2026-03-07T08:00 | 2026-04-08T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2888 | 175 | 1.1.2.2.4.3.1 | 7 | Column & Shear Wall | 2026-03-07T08:00 | 2026-03-18T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2889 | 176 | 1.1.2.2.4.3.1.1 | 8 | Reinforcement | 2026-03-07T08:00 | 2026-03-14T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 150FS | 177SS+3.0d
2890 | 177 | 1.1.2.2.4.3.1.2 | 8 | Shuttering | 2026-03-10T08:00 | 2026-03-15T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 176SS+3.0d | 178FS
2891 | 178 | 1.1.2.2.4.3.1.3 | 8 | Checking | 2026-03-16T08:00 | 2026-03-16T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 177FS | 179FS
2892 | 179 | 1.1.2.2.4.3.1.4 | 8 | Column & Shear wall Concrete | 2026-03-17T08:00 | 2026-03-18T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 178FS | 181FS
2893 | 180 | 1.1.2.2.4.3.2 | 7 | 1st Floor - Pour 3 | 2026-03-19T08:00 | 2026-04-08T20:00 | 19.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2894 | 181 | 1.1.2.2.4.3.2.1 | 8 | Slab Shuttering | 2026-03-19T08:00 | 2026-04-04T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 179FS | 182SS+7.0d
2895 | 182 | 1.1.2.2.4.3.2.2 | 8 | Reinforcement | 2026-03-28T08:00 | 2026-04-06T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 181SS+7.0d | 183FS
2896 | 183 | 1.1.2.2.4.3.2.3 | 8 | Checking | 2026-04-07T08:00 | 2026-04-07T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 182FS | 184FS
2897 | 184 | 1.1.2.2.4.3.2.4 | 8 | Slab Casting | 2026-04-08T08:00 | 2026-04-08T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 183FS | 186FF+2.0d, 185FS
2898 | 185 | 1.1.2.2.4.4 | 6 | Ground Floor Grade Slab / Trimix | 2026-04-13T08:00 | 2026-05-13T20:00 | 30.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 173FS, 162FS, 184FS
2899 | 186 | 1.1.2.2.5 | 5 | Receipt of Aluform Material | 2026-03-27T08:00 | 2026-04-10T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 184FF+2.0d | 189FS, 231FS
2900 | 187 | 1.1.2.3 | 4 | Super Structure - Typical Mivan Slabs | 2026-04-11T08:00 | 2027-09-23T20:00 | 511.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3172 | 188 | 1.1.2.3.1 | 5 | 2nd floor - (5th Slab Mockup) | 2026-04-11T08:00 | 2026-05-25T20:00 | 44.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3174 | 189 | 1.1.2.3.1.1 | 6 | Vertical Reinforcement Work | 2026-04-11T08:00 | 2026-04-18T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 186FS, 7FS, 8FS | 190FS
3175 | 190 | 1.1.2.3.1.2 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-04-19T08:00 | 2026-05-07T20:00 | 18.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 189FS | 191FS
3176 | 191 | 1.1.2.3.1.3 | 6 | Slab & Beam Reinforcement Work | 2026-05-08T08:00 | 2026-05-21T20:00 | 14.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 190FS | 192FS
3177 | 192 | 1.1.2.3.1.4 | 6 | Electrical Conduiting & Checking | 2026-05-22T08:00 | 2026-05-24T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 191FS | 193FS
3178 | 193 | 1.1.2.3.1.5 | 6 | Slab Casting | 2026-05-25T08:00 | 2026-05-25T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 192FS | 195FS
3179 | 194 | 1.1.2.3.2 | 5 | 3rd floor - (6th Slab) | 2026-05-26T08:00 | 2026-06-15T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3187 | 195 | 1.1.2.3.2.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-05-26T08:00 | 2026-05-26T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 193FS | 196FS
3180 | 196 | 1.1.2.3.2.2 | 6 | Vertical Reinforcement Work | 2026-05-28T08:00 | 2026-06-01T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 195FS | 197FS
3181 | 197 | 1.1.2.3.2.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-06-02T08:00 | 2026-06-05T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 196FS | 198FS
3182 | 198 | 1.1.2.3.2.4 | 6 | Slab & Beam Reinforcement Work | 2026-06-06T08:00 | 2026-06-12T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 197FS | 199FS
3183 | 199 | 1.1.2.3.2.5 | 6 | Electrical Conduiting & Checking | 2026-06-13T08:00 | 2026-06-14T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 198FS | 200FS
3184 | 200 | 1.1.2.3.2.6 | 6 | Slab Casting | 2026-06-15T08:00 | 2026-06-15T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 199FS | 202FS
3198 | 201 | 1.1.2.3.3 | 5 | 4th floor - (7th Slab) | 2026-06-16T08:00 | 2026-07-01T20:00 | 16.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3216 | 202 | 1.1.2.3.3.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-06-16T08:00 | 2026-06-16T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 200FS | 203FS
3199 | 203 | 1.1.2.3.3.2 | 6 | Vertical Reinforcement Work | 2026-06-17T08:00 | 2026-06-19T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 202FS | 204FS
3200 | 204 | 1.1.2.3.3.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-06-20T08:00 | 2026-06-23T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 203FS | 205FS
3201 | 205 | 1.1.2.3.3.4 | 6 | Slab & Beam Reinforcement Work | 2026-06-24T08:00 | 2026-06-28T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 204FS | 206FS
3202 | 206 | 1.1.2.3.3.5 | 6 | Electrical Conduiting & Checking | 2026-06-29T08:00 | 2026-06-30T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 205FS | 207FS
3203 | 207 | 1.1.2.3.3.6 | 6 | Slab Casting | 2026-07-01T08:00 | 2026-07-01T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 206FS | 209FS
3204 | 208 | 1.1.2.3.4 | 5 | 5th floor - (8th Slab) | 2026-07-02T08:00 | 2026-07-17T20:00 | 16.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3205 | 209 | 1.1.2.3.4.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-07-02T08:00 | 2026-07-02T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 207FS | 210FS
3206 | 210 | 1.1.2.3.4.2 | 6 | Vertical Reinforcement Work | 2026-07-03T08:00 | 2026-07-05T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 209FS | 211FS
3207 | 211 | 1.1.2.3.4.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-07-06T08:00 | 2026-07-09T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 210FS | 212FS
3208 | 212 | 1.1.2.3.4.4 | 6 | Slab & Beam Reinforcement Work | 2026-07-10T08:00 | 2026-07-14T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 211FS | 213FS
3209 | 213 | 1.1.2.3.4.5 | 6 | Electrical Conduiting & Checking | 2026-07-15T08:00 | 2026-07-16T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 212FS | 214FS
3210 | 214 | 1.1.2.3.4.6 | 6 | Slab Casting | 2026-07-17T08:00 | 2026-07-17T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 213FS | 216FS, 396FS
3211 | 215 | 1.1.2.3.5 | 5 | 6th floor - (9th Slab) | 2026-07-18T08:00 | 2026-07-29T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3212 | 216 | 1.1.2.3.5.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-07-18T08:00 | 2026-07-18T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 214FS | 217SS
3213 | 217 | 1.1.2.3.5.2 | 6 | Vertical Reinforcement Work | 2026-07-18T08:00 | 2026-07-19T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 216SS | 218FF+3.0d
3214 | 218 | 1.1.2.3.5.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-07-19T08:00 | 2026-07-22T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 217FF+3.0d | 219FS
3215 | 219 | 1.1.2.3.5.4 | 6 | Slab & Beam Reinforcement Work | 2026-07-23T08:00 | 2026-07-26T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 218FS | 220FS
3189 | 220 | 1.1.2.3.5.5 | 6 | Electrical Conduiting & Checking | 2026-07-27T08:00 | 2026-07-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 219FS | 221FS
3190 | 221 | 1.1.2.3.5.6 | 6 | Slab Casting | 2026-07-29T08:00 | 2026-07-29T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 220FS | 223FS
3191 | 222 | 1.1.2.3.6 | 5 | 7th floor - (10th Slab - Refuge Floor) | 2026-07-30T08:00 | 2026-08-19T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3192 | 223 | 1.1.2.3.6.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-07-30T08:00 | 2026-07-30T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 221FS | 224FS
3193 | 224 | 1.1.2.3.6.2 | 6 | Vertical Reinforcement Work | 2026-07-31T08:00 | 2026-08-04T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 223FS | 225FS
3194 | 225 | 1.1.2.3.6.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-08-05T08:00 | 2026-08-08T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 224FS | 226FS
3195 | 226 | 1.1.2.3.6.4 | 6 | Slab & Beam Reinforcement Work | 2026-08-09T08:00 | 2026-08-16T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 225FS | 227FS
3196 | 227 | 1.1.2.3.6.5 | 6 | Electrical Conduiting & Checking | 2026-08-17T08:00 | 2026-08-18T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 226FS | 228FS
3197 | 228 | 1.1.2.3.6.6 | 6 | Slab Casting | 2026-08-19T08:00 | 2026-08-19T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 227FS | 230FS, 398FS
3185 | 229 | 1.1.2.3.7 | 5 | 8th floor - (11th Slab) | 2026-08-20T08:00 | 2026-08-31T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3186 | 230 | 1.1.2.3.7.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-08-20T08:00 | 2026-08-20T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 228FS | 231SS
2901 | 231 | 1.1.2.3.7.2 | 6 | Vertical Reinforcement Work | 2026-08-20T08:00 | 2026-08-21T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 230SS, 186FS | 232FF+3.0d
2902 | 232 | 1.1.2.3.7.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-08-21T08:00 | 2026-08-24T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 231FF+3.0d | 233FS
2903 | 233 | 1.1.2.3.7.4 | 6 | Slab & Beam Reinforcement Work | 2026-08-25T08:00 | 2026-08-28T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 232FS | 234FS
2904 | 234 | 1.1.2.3.7.5 | 6 | Electrical Conduiting & Checking | 2026-08-29T08:00 | 2026-08-30T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 233FS | 235FS
2905 | 235 | 1.1.2.3.7.6 | 6 | Slab Casting | 2026-08-31T08:00 | 2026-08-31T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 234FS | 237FS
2908 | 236 | 1.1.2.3.8 | 5 | 9th floor - (12th Slab) | 2026-09-01T08:00 | 2026-09-12T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
2909 | 237 | 1.1.2.3.8.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-09-01T08:00 | 2026-09-01T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 235FS | 238SS
2910 | 238 | 1.1.2.3.8.2 | 6 | Vertical Reinforcement Work | 2026-09-01T08:00 | 2026-09-02T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 237SS | 239FF+3.0d
2911 | 239 | 1.1.2.3.8.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-09-02T08:00 | 2026-09-05T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 238FF+3.0d | 240FS
2912 | 240 | 1.1.2.3.8.4 | 6 | Slab & Beam Reinforcement Work | 2026-09-06T08:00 | 2026-09-09T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 239FS | 241FS
2913 | 241 | 1.1.2.3.8.5 | 6 | Electrical Conduiting & Checking | 2026-09-10T08:00 | 2026-09-11T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 240FS | 242FS
3265 | 242 | 1.1.2.3.8.6 | 6 | Slab Casting | 2026-09-12T08:00 | 2026-09-12T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 241FS | 244FS
2914 | 243 | 1.1.2.3.9 | 5 | 10th floor - (13th Slab) | 2026-09-13T08:00 | 2026-09-26T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3217 | 244 | 1.1.2.3.9.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-09-13T08:00 | 2026-09-13T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 242FS | 245SS
3218 | 245 | 1.1.2.3.9.2 | 6 | Vertical Reinforcement Work | 2026-09-13T08:00 | 2026-09-15T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 244SS | 246FF+3.0d
3219 | 246 | 1.1.2.3.9.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-09-15T08:00 | 2026-09-19T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 245FF+3.0d | 247FS
3220 | 247 | 1.1.2.3.9.4 | 6 | Slab & Beam Reinforcement Work | 2026-09-20T08:00 | 2026-09-23T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 246FS | 248FS
3221 | 248 | 1.1.2.3.9.5 | 6 | Electrical Conduiting & Checking | 2026-09-24T08:00 | 2026-09-25T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 247FS | 249FS
3222 | 249 | 1.1.2.3.9.6 | 6 | Slab Casting | 2026-09-26T08:00 | 2026-09-26T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 248FS | 251FS
3223 | 250 | 1.1.2.3.10 | 5 | 11th floor - (14th Slab) | 2026-09-27T08:00 | 2026-10-08T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3224 | 251 | 1.1.2.3.10.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-09-27T08:00 | 2026-09-27T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 249FS | 252SS
3225 | 252 | 1.1.2.3.10.2 | 6 | Vertical Reinforcement Work | 2026-09-27T08:00 | 2026-09-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 251SS | 253FF+3.0d
3226 | 253 | 1.1.2.3.10.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-09-28T08:00 | 2026-10-01T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 252FF+3.0d | 254FS
3227 | 254 | 1.1.2.3.10.4 | 6 | Slab & Beam Reinforcement Work | 2026-10-02T08:00 | 2026-10-05T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 253FS | 255FS
3228 | 255 | 1.1.2.3.10.5 | 6 | Electrical Conduiting & Checking | 2026-10-06T08:00 | 2026-10-07T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 254FS | 256FS
3247 | 256 | 1.1.2.3.10.6 | 6 | Slab Casting | 2026-10-08T08:00 | 2026-10-08T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 255FS | 258FS
3248 | 257 | 1.1.2.3.11 | 5 | 12th floor - (15th Slab - Refuge Floor) | 2026-10-09T08:00 | 2026-10-30T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3249 | 258 | 1.1.2.3.11.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-10-09T08:00 | 2026-10-09T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 256FS | 259FS
3250 | 259 | 1.1.2.3.11.2 | 6 | Vertical Reinforcement Work | 2026-10-10T08:00 | 2026-10-14T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 258FS | 260FS
3251 | 260 | 1.1.2.3.11.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-10-15T08:00 | 2026-10-18T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 259FS | 261FS
3252 | 261 | 1.1.2.3.11.4 | 6 | Slab & Beam Reinforcement Work | 2026-10-19T08:00 | 2026-10-27T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 260FS | 262FS
3253 | 262 | 1.1.2.3.11.5 | 6 | Electrical Conduiting & Checking | 2026-10-28T08:00 | 2026-10-29T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 261FS | 263FS
3254 | 263 | 1.1.2.3.11.6 | 6 | Slab Casting | 2026-10-30T08:00 | 2026-10-30T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 262FS | 265FS, 407FS
3255 | 264 | 1.1.2.3.12 | 5 | 13th floor - (16th Slab) | 2026-10-31T08:00 | 2026-11-14T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3256 | 265 | 1.1.2.3.12.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-10-31T08:00 | 2026-10-31T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 263FS | 266SS
3257 | 266 | 1.1.2.3.12.2 | 6 | Vertical Reinforcement Work | 2026-10-31T08:00 | 2026-11-01T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 265SS | 267FF+3.0d
3258 | 267 | 1.1.2.3.12.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-11-01T08:00 | 2026-11-04T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 266FF+3.0d | 268FS
3259 | 268 | 1.1.2.3.12.4 | 6 | Slab & Beam Reinforcement Work | 2026-11-05T08:00 | 2026-11-08T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 267FS | 269FS
3260 | 269 | 1.1.2.3.12.5 | 6 | Electrical Conduiting & Checking | 2026-11-12T08:00 | 2026-11-13T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 268FS | 270FS
3261 | 270 | 1.1.2.3.12.6 | 6 | Slab Casting | 2026-11-14T08:00 | 2026-11-14T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 269FS | 272FS
3262 | 271 | 1.1.2.3.13 | 5 | 14th floor - (17th Slab) | 2026-11-15T08:00 | 2026-11-26T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3263 | 272 | 1.1.2.3.13.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-11-15T08:00 | 2026-11-15T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 270FS | 273SS
3264 | 273 | 1.1.2.3.13.2 | 6 | Vertical Reinforcement Work | 2026-11-15T08:00 | 2026-11-16T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 272SS | 274FF+3.0d
3238 | 274 | 1.1.2.3.13.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-11-16T08:00 | 2026-11-19T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 273FF+3.0d | 275FS
3239 | 275 | 1.1.2.3.13.4 | 6 | Slab & Beam Reinforcement Work | 2026-11-20T08:00 | 2026-11-23T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 274FS | 276FS
3240 | 276 | 1.1.2.3.13.5 | 6 | Electrical Conduiting & Checking | 2026-11-24T08:00 | 2026-11-25T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 275FS | 277FS
3241 | 277 | 1.1.2.3.13.6 | 6 | Slab Casting | 2026-11-26T08:00 | 2026-11-26T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 276FS | 279FS
3242 | 278 | 1.1.2.3.14 | 5 | 15th floor - (18th Slab) | 2026-11-27T08:00 | 2026-12-08T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3243 | 279 | 1.1.2.3.14.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-11-27T08:00 | 2026-11-27T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 277FS | 280SS
3244 | 280 | 1.1.2.3.14.2 | 6 | Vertical Reinforcement Work | 2026-11-27T08:00 | 2026-11-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 279SS | 281FF+3.0d
3245 | 281 | 1.1.2.3.14.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-11-28T08:00 | 2026-12-01T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 280FF+3.0d | 282FS
3246 | 282 | 1.1.2.3.14.4 | 6 | Slab & Beam Reinforcement Work | 2026-12-02T08:00 | 2026-12-05T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 281FS | 283FS
3230 | 283 | 1.1.2.3.14.5 | 6 | Electrical Conduiting & Checking | 2026-12-06T08:00 | 2026-12-07T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 282FS | 284FS
3231 | 284 | 1.1.2.3.14.6 | 6 | Slab Casting | 2026-12-08T08:00 | 2026-12-08T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 283FS | 286FS
3232 | 285 | 1.1.2.3.15 | 5 | 16th floor - (19th Slab) | 2026-12-09T08:00 | 2026-12-20T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3233 | 286 | 1.1.2.3.15.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-12-09T08:00 | 2026-12-09T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 284FS | 287SS
3234 | 287 | 1.1.2.3.15.2 | 6 | Vertical Reinforcement Work | 2026-12-09T08:00 | 2026-12-10T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 286SS | 288FF+3.0d
3235 | 288 | 1.1.2.3.15.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-12-10T08:00 | 2026-12-13T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 287FF+3.0d | 289FS
3229 | 289 | 1.1.2.3.15.4 | 6 | Slab & Beam Reinforcement Work | 2026-12-14T08:00 | 2026-12-17T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 288FS | 290FS
3236 | 290 | 1.1.2.3.15.5 | 6 | Electrical Conduiting & Checking | 2026-12-18T08:00 | 2026-12-19T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 289FS | 291FS
3324 | 291 | 1.1.2.3.15.6 | 6 | Slab Casting | 2026-12-20T08:00 | 2026-12-20T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 290FS | 293FS
3237 | 292 | 1.1.2.3.16 | 5 | 17th floor - (20th Slab - Refuge Floor) | 2026-12-21T08:00 | 2027-01-09T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3287 | 293 | 1.1.2.3.16.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2026-12-21T08:00 | 2026-12-21T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 291FS | 294FS
3288 | 294 | 1.1.2.3.16.2 | 6 | Vertical Reinforcement Work | 2026-12-22T08:00 | 2026-12-26T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 293FS | 295FS
3289 | 295 | 1.1.2.3.16.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2026-12-27T08:00 | 2026-12-30T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 294FS | 296FS
3290 | 296 | 1.1.2.3.16.4 | 6 | Slab & Beam Reinforcement Work | 2026-12-31T08:00 | 2027-01-06T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 295FS | 297FS
3291 | 297 | 1.1.2.3.16.5 | 6 | Electrical Conduiting & Checking | 2027-01-07T08:00 | 2027-01-08T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 296FS | 298FS
3292 | 298 | 1.1.2.3.16.6 | 6 | Slab Casting | 2027-01-09T08:00 | 2027-01-09T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 297FS | 300FS
3293 | 299 | 1.1.2.3.17 | 5 | 18th floor - (21st Slab) | 2027-01-10T08:00 | 2027-01-21T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3294 | 300 | 1.1.2.3.17.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-01-10T08:00 | 2027-01-10T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 298FS | 301SS
3295 | 301 | 1.1.2.3.17.2 | 6 | Vertical Reinforcement Work | 2027-01-10T08:00 | 2027-01-11T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 300SS | 302FF+3.0d
3296 | 302 | 1.1.2.3.17.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-01-11T08:00 | 2027-01-14T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 301FF+3.0d | 303FS
3297 | 303 | 1.1.2.3.17.4 | 6 | Slab & Beam Reinforcement Work | 2027-01-15T08:00 | 2027-01-18T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 302FS | 304FS
3298 | 304 | 1.1.2.3.17.5 | 6 | Electrical Conduiting & Checking | 2027-01-19T08:00 | 2027-01-20T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 303FS | 305FS
3299 | 305 | 1.1.2.3.17.6 | 6 | Slab Casting | 2027-01-21T08:00 | 2027-01-21T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 304FS | 307FS, 409FS
3300 | 306 | 1.1.2.3.18 | 5 | 19th floor - (22nd Slab) | 2027-01-22T08:00 | 2027-02-03T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3301 | 307 | 1.1.2.3.18.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-01-22T08:00 | 2027-01-22T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 305FS | 308SS
3302 | 308 | 1.1.2.3.18.2 | 6 | Vertical Reinforcement Work | 2027-01-22T08:00 | 2027-01-23T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 307SS | 309FF+3.0d
3303 | 309 | 1.1.2.3.18.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-01-23T08:00 | 2027-01-27T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 308FF+3.0d | 310FS
3304 | 310 | 1.1.2.3.18.4 | 6 | Slab & Beam Reinforcement Work | 2027-01-28T08:00 | 2027-01-31T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 309FS | 311FS
3305 | 311 | 1.1.2.3.18.5 | 6 | Electrical Conduiting & Checking | 2027-02-01T08:00 | 2027-02-02T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 310FS | 312FS
3306 | 312 | 1.1.2.3.18.6 | 6 | Slab Casting | 2027-02-03T08:00 | 2027-02-03T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 311FS | 314FS, 410FS
3307 | 313 | 1.1.2.3.19 | 5 | 20th floor - (23rd Slab) | 2027-02-04T08:00 | 2027-02-15T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3308 | 314 | 1.1.2.3.19.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-02-04T08:00 | 2027-02-04T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 312FS | 315SS
3309 | 315 | 1.1.2.3.19.2 | 6 | Vertical Reinforcement Work | 2027-02-04T08:00 | 2027-02-05T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 314SS | 316FF+3.0d
3310 | 316 | 1.1.2.3.19.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-02-05T08:00 | 2027-02-08T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 315FF+3.0d | 317FS
3311 | 317 | 1.1.2.3.19.4 | 6 | Slab & Beam Reinforcement Work | 2027-02-09T08:00 | 2027-02-12T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 316FS | 318FS
3312 | 318 | 1.1.2.3.19.5 | 6 | Electrical Conduiting & Checking | 2027-02-13T08:00 | 2027-02-14T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 317FS | 319FS
3325 | 319 | 1.1.2.3.19.6 | 6 | Slab Casting | 2027-02-15T08:00 | 2027-02-15T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 318FS | 321FS
3313 | 320 | 1.1.2.3.20 | 5 | 21st floor - (24th Slab - Refuge Floor) | 2027-02-16T08:00 | 2027-03-07T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3314 | 321 | 1.1.2.3.20.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-02-16T08:00 | 2027-02-16T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 319FS | 322FS
3315 | 322 | 1.1.2.3.20.2 | 6 | Vertical Reinforcement Work | 2027-02-17T08:00 | 2027-02-21T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 321FS | 323FS
3316 | 323 | 1.1.2.3.20.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-02-22T08:00 | 2027-02-25T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 322FS | 324FS
3317 | 324 | 1.1.2.3.20.4 | 6 | Slab & Beam Reinforcement Work | 2027-02-26T08:00 | 2027-03-04T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 323FS | 325FS
3318 | 325 | 1.1.2.3.20.5 | 6 | Electrical Conduiting & Checking | 2027-03-05T08:00 | 2027-03-06T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 324FS | 326FS
3319 | 326 | 1.1.2.3.20.6 | 6 | Slab Casting | 2027-03-07T08:00 | 2027-03-07T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 325FS | 328FS
3320 | 327 | 1.1.2.3.21 | 5 | 22nd floor - (25th Slab) | 2027-03-08T08:00 | 2027-03-21T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3321 | 328 | 1.1.2.3.21.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-03-08T08:00 | 2027-03-08T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 326FS | 329SS
3322 | 329 | 1.1.2.3.21.2 | 6 | Vertical Reinforcement Work | 2027-03-08T08:00 | 2027-03-09T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 328SS | 330FF+3.0d
3323 | 330 | 1.1.2.3.21.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-03-09T08:00 | 2027-03-14T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 329FF+3.0d | 331FS
3266 | 331 | 1.1.2.3.21.4 | 6 | Slab & Beam Reinforcement Work | 2027-03-15T08:00 | 2027-03-18T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 330FS | 332FS
3267 | 332 | 1.1.2.3.21.5 | 6 | Electrical Conduiting & Checking | 2027-03-19T08:00 | 2027-03-20T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 331FS | 333FS
3268 | 333 | 1.1.2.3.21.6 | 6 | Slab Casting | 2027-03-21T08:00 | 2027-03-21T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 332FS | 335FS, 414FS
3269 | 334 | 1.1.2.3.22 | 5 | 23rd floor - (26th Slab) | 2027-03-25T08:00 | 2027-04-05T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3270 | 335 | 1.1.2.3.22.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-03-25T08:00 | 2027-03-25T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 333FS | 336SS
3271 | 336 | 1.1.2.3.22.2 | 6 | Vertical Reinforcement Work | 2027-03-25T08:00 | 2027-03-26T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 335SS | 337FF+3.0d
3272 | 337 | 1.1.2.3.22.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-03-26T08:00 | 2027-03-29T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 336FF+3.0d | 338FS
3273 | 338 | 1.1.2.3.22.4 | 6 | Slab & Beam Reinforcement Work | 2027-03-30T08:00 | 2027-04-02T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 337FS | 339FS
3274 | 339 | 1.1.2.3.22.5 | 6 | Electrical Conduiting & Checking | 2027-04-03T08:00 | 2027-04-04T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 338FS | 340FS
3275 | 340 | 1.1.2.3.22.6 | 6 | Slab Casting | 2027-04-05T08:00 | 2027-04-05T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 339FS | 342FS, 415FS
3276 | 341 | 1.1.2.3.23 | 5 | 24th floor - (27th Slab) | 2027-04-06T08:00 | 2027-04-17T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3277 | 342 | 1.1.2.3.23.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-04-06T08:00 | 2027-04-06T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 340FS | 343SS
3278 | 343 | 1.1.2.3.23.2 | 6 | Vertical Reinforcement Work | 2027-04-06T08:00 | 2027-04-07T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 342SS | 344FF+3.0d
3279 | 344 | 1.1.2.3.23.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-04-07T08:00 | 2027-04-10T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 343FF+3.0d | 345FS
3280 | 345 | 1.1.2.3.23.4 | 6 | Slab & Beam Reinforcement Work | 2027-04-11T08:00 | 2027-04-14T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 344FS | 346FS
3281 | 346 | 1.1.2.3.23.5 | 6 | Electrical Conduiting & Checking | 2027-04-15T08:00 | 2027-04-16T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 345FS | 347FS
3326 | 347 | 1.1.2.3.23.6 | 6 | Slab Casting | 2027-04-17T08:00 | 2027-04-17T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 346FS | 349FS, 416FS
3327 | 348 | 1.1.2.3.24 | 5 | 25th floor - (28th Slab) | 2027-04-18T08:00 | 2027-04-29T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3328 | 349 | 1.1.2.3.24.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-04-18T08:00 | 2027-04-18T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 347FS | 350SS
3329 | 350 | 1.1.2.3.24.2 | 6 | Vertical Reinforcement Work | 2027-04-18T08:00 | 2027-04-19T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 349SS | 351FF+3.0d
3330 | 351 | 1.1.2.3.24.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-04-19T08:00 | 2027-04-22T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 350FF+3.0d | 352FS
3331 | 352 | 1.1.2.3.24.4 | 6 | Slab & Beam Reinforcement Work | 2027-04-23T08:00 | 2027-04-26T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 351FS | 353FS
3332 | 353 | 1.1.2.3.24.5 | 6 | Electrical Conduiting & Checking | 2027-04-27T08:00 | 2027-04-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 352FS | 354FS
3333 | 354 | 1.1.2.3.24.6 | 6 | Slab Casting | 2027-04-29T08:00 | 2027-04-29T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 353FS | 356FS, 417FS
3334 | 355 | 1.1.2.3.25 | 5 | 26th floor - (29th Slab - Refuge Floor) | 2027-04-30T08:00 | 2027-05-21T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3335 | 356 | 1.1.2.3.25.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-04-30T08:00 | 2027-04-30T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 354FS | 357FS
3336 | 357 | 1.1.2.3.25.2 | 6 | Vertical Reinforcement Work | 2027-05-02T08:00 | 2027-05-06T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 356FS | 358FS
3337 | 358 | 1.1.2.3.25.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-05-07T08:00 | 2027-05-10T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 357FS | 359FS
3338 | 359 | 1.1.2.3.25.4 | 6 | Slab & Beam Reinforcement Work | 2027-05-11T08:00 | 2027-05-18T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 358FS | 360FS
3339 | 360 | 1.1.2.3.25.5 | 6 | Electrical Conduiting & Checking | 2027-05-19T08:00 | 2027-05-20T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 359FS | 361FS
3340 | 361 | 1.1.2.3.25.6 | 6 | Slab Casting | 2027-05-21T08:00 | 2027-05-21T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 360FS | 363FS, 418FS
3341 | 362 | 1.1.2.3.26 | 5 | 27th floor - (30th Slab) | 2027-05-22T08:00 | 2027-06-02T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3342 | 363 | 1.1.2.3.26.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-05-22T08:00 | 2027-05-22T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 361FS | 364SS
3343 | 364 | 1.1.2.3.26.2 | 6 | Vertical Reinforcement Work | 2027-05-22T08:00 | 2027-05-23T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 363SS | 365FF+3.0d
3344 | 365 | 1.1.2.3.26.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-05-23T08:00 | 2027-05-26T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 364FF+3.0d | 366FS
3345 | 366 | 1.1.2.3.26.4 | 6 | Slab & Beam Reinforcement Work | 2027-05-27T08:00 | 2027-05-30T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 365FS | 367FS
3346 | 367 | 1.1.2.3.26.5 | 6 | Electrical Conduiting & Checking | 2027-05-31T08:00 | 2027-06-01T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 366FS | 368FS
3347 | 368 | 1.1.2.3.26.6 | 6 | Slab Casting | 2027-06-02T08:00 | 2027-06-02T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 367FS | 370FS, 419FS
3348 | 369 | 1.1.2.3.27 | 5 | 28th floor - (31st Slab) | 2027-06-03T08:00 | 2027-06-14T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3349 | 370 | 1.1.2.3.27.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-06-03T08:00 | 2027-06-03T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 368FS | 371SS
3350 | 371 | 1.1.2.3.27.2 | 6 | Vertical Reinforcement Work | 2027-06-03T08:00 | 2027-06-04T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 370SS | 372FF+3.0d
3351 | 372 | 1.1.2.3.27.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-06-04T08:00 | 2027-06-07T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 371FF+3.0d | 373FS
3282 | 373 | 1.1.2.3.27.4 | 6 | Slab & Beam Reinforcement Work | 2027-06-08T08:00 | 2027-06-11T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 372FS | 374FS
3283 | 374 | 1.1.2.3.27.5 | 6 | Electrical Conduiting & Checking | 2027-06-12T08:00 | 2027-06-13T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 373FS | 375FS
3284 | 375 | 1.1.2.3.27.6 | 6 | Slab Casting | 2027-06-14T08:00 | 2027-06-14T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 374FS | 377FS, 420FS
3285 | 376 | 1.1.2.3.28 | 5 | 29th floor - (32nd Slab) | 2027-06-15T08:00 | 2027-06-26T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3286 | 377 | 1.1.2.3.28.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-06-15T08:00 | 2027-06-15T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 375FS | 378SS
2916 | 378 | 1.1.2.3.28.2 | 6 | Vertical Reinforcement Work | 2027-06-15T08:00 | 2027-06-16T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 377SS | 379FF+3.0d
2917 | 379 | 1.1.2.3.28.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-06-16T08:00 | 2027-06-19T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 378FF+3.0d | 380FS
2918 | 380 | 1.1.2.3.28.4 | 6 | Slab & Beam Reinforcement Work | 2027-06-20T08:00 | 2027-06-23T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 379FS | 381FS
2919 | 381 | 1.1.2.3.28.5 | 6 | Electrical Conduiting & Checking | 2027-06-24T08:00 | 2027-06-25T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 380FS | 382FS
2920 | 382 | 1.1.2.3.28.6 | 6 | Slab Casting | 2027-06-26T08:00 | 2027-06-26T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 381FS | 384FS, 421FS
3352 | 383 | 1.1.2.3.29 | 5 | Terrace floor - (33rd Slab) | 2027-06-27T08:00 | 2027-07-08T20:00 | 12.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3353 | 384 | 1.1.2.3.29.1 | 6 | Deshuttering of Vertical, Grid Marking & Bracket Fixing | 2027-06-27T08:00 | 2027-06-27T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 382FS | 385SS
3354 | 385 | 1.1.2.3.29.2 | 6 | Vertical Reinforcement Work | 2027-06-27T08:00 | 2027-06-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 384SS | 386FF+3.0d
3355 | 386 | 1.1.2.3.29.3 | 6 | Shuttering for Column, Wall, Beam & Slab | 2027-06-28T08:00 | 2027-07-01T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 385FF+3.0d | 387FS
3356 | 387 | 1.1.2.3.29.4 | 6 | Slab & Beam Reinforcement Work | 2027-07-02T08:00 | 2027-07-05T20:00 | 4.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 386FS | 388FS
3357 | 388 | 1.1.2.3.29.5 | 6 | Electrical Conduiting & Checking | 2027-07-06T08:00 | 2027-07-07T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 387FS | 389FS
3358 | 389 | 1.1.2.3.29.6 | 6 | Slab Casting | 2027-07-08T08:00 | 2027-07-08T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 388FS | 391FS, 392FS+5.0d, 422FS
2937 | 390 | 1.1.2.3.30 | 5 | Above Terrace work | 2027-07-09T08:00 | 2027-09-23T20:00 | 75.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2938 | 391 | 1.1.2.3.30.1 | 6 | Parapet Wall | 2027-07-09T08:00 | 2027-08-07T20:00 | 30.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 389FS | 394FS, 425FS+7.0d
2939 | 392 | 1.1.2.3.30.2 | 6 | LMR Bottom Slab | 2027-07-14T08:00 | 2027-08-07T20:00 | 25.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 389FS+5.0d | 393FS+2.0d
2940 | 393 | 1.1.2.3.30.3 | 6 | LMR Top Slab | 2027-08-10T08:00 | 2027-09-07T20:00 | 28.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 392FS+2.0d | 394FF-30.0d
2941 | 394 | 1.1.2.3.30.4 | 6 | Elevation Pargola Work | 2027-08-08T08:00 | 2027-09-23T20:00 | 45.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 391FS, 393FF-30.0d
2942 | 395 | 1.1.2.4 | 4 | Post Pour - Tower 1 | 2026-07-18T08:00 | 2027-11-19T20:00 | 468.0d | 0.0 |  |  |  |  | False | True | True | AS_SOON_AS_POSSIBLE
3017 | 396 | 1.1.2.4.1 | 5 | 1st Floor | 2026-07-18T08:00 | 2026-07-29T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 214FS | 397FS+2.0d
3016 | 397 | 1.1.2.4.2 | 5 | 2nd floor | 2026-08-01T08:00 | 2026-08-12T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 396FS+2.0d | 398FS
3015 | 398 | 1.1.2.4.3 | 5 | 3rd floor | 2026-08-20T08:00 | 2026-08-31T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 397FS, 228FS | 399FS+1.0d
3014 | 399 | 1.1.2.4.4 | 5 | 4th floor | 2026-09-02T08:00 | 2026-09-13T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 398FS+1.0d | 400FS+2.0d
3013 | 400 | 1.1.2.4.5 | 5 | 5th floor | 2026-09-18T08:00 | 2026-09-29T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 399FS+2.0d | 401FS+1.0d
3012 | 401 | 1.1.2.4.6 | 5 | 6th floor | 2026-10-01T08:00 | 2026-10-12T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 400FS+1.0d | 402FS+2.0d
3011 | 402 | 1.1.2.4.7 | 5 | 7th Refuge floor | 2026-10-15T08:00 | 2026-10-28T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 401FS+2.0d | 403FS+1.0d
3010 | 403 | 1.1.2.4.8 | 5 | 8th floor | 2026-10-30T08:00 | 2026-11-13T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 402FS+1.0d | 404FS+1.0d
3009 | 404 | 1.1.2.4.9 | 5 | 9th floor | 2026-11-15T08:00 | 2026-11-26T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 403FS+1.0d | 405FS+1.0d
3008 | 405 | 1.1.2.4.10 | 5 | 10th floor | 2026-11-28T08:00 | 2026-12-09T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 404FS+1.0d | 406FS+1.0d
3007 | 406 | 1.1.2.4.11 | 5 | 11th floor | 2026-12-11T08:00 | 2026-12-22T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 405FS+1.0d | 407FS+1.0d
3018 | 407 | 1.1.2.4.12 | 5 | 12th Refuge floor | 2026-12-24T08:00 | 2027-01-04T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 406FS+1.0d, 263FS | 408FS+1.0d
3019 | 408 | 1.1.2.4.13 | 5 | 13th floor | 2027-01-06T08:00 | 2027-01-17T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 407FS+1.0d | 409FS+1.0d
3020 | 409 | 1.1.2.4.14 | 5 | 14th floor | 2027-01-22T08:00 | 2027-02-03T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 408FS+1.0d, 305FS | 410FS+1.0d
3006 | 410 | 1.1.2.4.15 | 5 | 15th floor | 2027-02-05T08:00 | 2027-02-16T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 409FS+1.0d, 312FS | 411FS+1.0d
3005 | 411 | 1.1.2.4.16 | 5 | 16th floor | 2027-02-18T08:00 | 2027-03-01T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 410FS+1.0d | 412FS+1.0d
3004 | 412 | 1.1.2.4.17 | 5 | 17th Refuge floor | 2027-03-03T08:00 | 2027-03-16T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 411FS+1.0d | 413FS+1.0d
3003 | 413 | 1.1.2.4.18 | 5 | 18th floor | 2027-03-18T08:00 | 2027-04-01T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 412FS+1.0d | 414FS+1.0d
3040 | 414 | 1.1.2.4.19 | 5 | 19th floor | 2027-04-03T08:00 | 2027-04-14T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 413FS+1.0d, 333FS | 415FS+1.0d
3039 | 415 | 1.1.2.4.20 | 5 | 20th floor | 2027-04-16T08:00 | 2027-04-27T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 414FS+1.0d, 340FS | 416FS+1.0d
3038 | 416 | 1.1.2.4.21 | 5 | 21st Refuge floor | 2027-04-29T08:00 | 2027-05-11T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 415FS+1.0d, 347FS | 417FS+1.0d
3037 | 417 | 1.1.2.4.22 | 5 | 22nd floor | 2027-05-13T08:00 | 2027-05-25T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 416FS+1.0d, 354FS | 418FS
3036 | 418 | 1.1.2.4.23 | 5 | 23rd floor | 2027-05-26T08:00 | 2027-06-06T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 417FS, 361FS | 419FS
3035 | 419 | 1.1.2.4.24 | 5 | 24th floor | 2027-06-07T08:00 | 2027-06-18T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 418FS, 368FS | 420FS+1.0d
3034 | 420 | 1.1.2.4.25 | 5 | 25th floor | 2027-06-20T08:00 | 2027-07-01T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 419FS+1.0d, 375FS | 421FS+1.0d
3033 | 421 | 1.1.2.4.26 | 5 | 26th Refuge floor | 2027-07-03T08:00 | 2027-07-14T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 420FS+1.0d, 382FS | 422FS+1.0d
3032 | 422 | 1.1.2.4.27 | 5 | 27th floor | 2027-07-16T08:00 | 2027-07-27T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 421FS+1.0d, 389FS | 423FS+1.0d
3031 | 423 | 1.1.2.4.28 | 5 | 28th floor | 2027-07-29T08:00 | 2027-08-09T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 422FS+1.0d | 424FS+2.0d
3030 | 424 | 1.1.2.4.29 | 5 | 29th floor | 2027-08-12T08:00 | 2027-08-23T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 423FS+2.0d | 425SS+4.0d
3101 | 425 | 1.1.2.4.30 | 5 | External Post Pour work | 2027-08-16T08:00 | 2027-11-19T20:00 | 90.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 391FS+7.0d, 424SS+4.0d | 426FS+1.0d
2943 | 426 | 1.1.3 | 3 | Handover | 2027-11-21T08:00 | 2027-12-10T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | True | AS_SOON_AS_POSSIBLE |  | 425FS+1.0d
1284 | 427 | 1.1.4 | 3 | Tower 1 Schedule - for NTA | 2025-10-19T08:00 | 2026-06-30T20:00 | 243.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1286 | 428 | 1.1.4.1 | 4 | Foundation | 2025-10-19T08:00 | 2025-12-06T20:00 | 45.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2674 | 429 | 1.1.4.1.1 | 5 | South Side NTA | 2025-10-19T08:00 | 2025-12-02T20:00 | 41.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3360 | 430 | 1.1.4.1.1.1 | 6 | Dressing | 2025-10-19T08:00 | 2025-10-24T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 6FS, 7FS | 431FS, 440SS+2.0d, 450SS+4.0d
3359 | 431 | 1.1.4.1.1.2 | 6 | PCC | 2025-10-25T08:00 | 2025-10-26T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 430FS | 432FS
2675 | 432 | 1.1.4.1.1.3 | 6 | Rock Anchoring 28 Nos - Client Scope | 2025-10-27T08:00 | 2025-11-05T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 431FS | 433SS+8.0d, 442SS+6.0d
2676 | 433 | 1.1.4.1.1.4 | 6 | Waterproofing - Client Scope | 2025-11-04T08:00 | 2025-11-08T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 432SS+8.0d | 434SS+3.0d
2677 | 434 | 1.1.4.1.1.5 | 6 | Raft RF (Incl Footing, SW, RW & Tie Beam) | 2025-11-11T08:00 | 2025-11-22T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 433SS+3.0d, 7FS, 8FS | 435SS+9.0d
2678 | 435 | 1.1.4.1.1.6 | 6 | Shuttering | 2025-11-20T08:00 | 2025-11-27T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 434SS+9.0d | 436FS
2679 | 436 | 1.1.4.1.1.7 | 6 | Checking | 2025-11-28T08:00 | 2025-11-28T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 435FS | 437FS
2680 | 437 | 1.1.4.1.1.8 | 6 | Raft Concrete - South side | 2025-11-29T08:00 | 2025-11-30T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 436FS | 438FS
2681 | 438 | 1.1.4.1.1.9 | 6 | Footing & Tie beam Shuttering & Concrete | 2025-12-01T08:00 | 2025-12-02T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 437FS | 464FS
1287 | 439 | 1.1.4.1.2 | 5 | East Side NTA | 2025-10-25T08:00 | 2025-12-01T20:00 | 38.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3361 | 440 | 1.1.4.1.2.1 | 6 | Dressing | 2025-10-25T08:00 | 2025-10-26T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 430SS+2.0d | 441FS
3362 | 441 | 1.1.4.1.2.2 | 6 | PCC | 2025-10-27T08:00 | 2025-10-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 440FS | 442FS
1288 | 442 | 1.1.4.1.2.3 | 6 | Rock Anchoring 9 Nos - Client Scope | 2025-11-02T08:00 | 2025-11-11T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 432SS+6.0d, 441FS | 443SS+5.0d, 453SS+5.0d
1289 | 443 | 1.1.4.1.2.4 | 6 | Waterproofing - Client Scope | 2025-11-07T08:00 | 2025-11-11T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 442SS+5.0d | 444SS+3.0d
1290 | 444 | 1.1.4.1.2.5 | 6 | Raft RF (Incl Footing, SW, RW & Tie Beam) | 2025-11-10T08:00 | 2025-11-21T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 443SS+3.0d | 445SS+9.0d
1291 | 445 | 1.1.4.1.2.6 | 6 | Shuttering | 2025-11-19T08:00 | 2025-11-26T20:00 | 8.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 444SS+9.0d | 446FS
1292 | 446 | 1.1.4.1.2.7 | 6 | Checking | 2025-11-27T08:00 | 2025-11-27T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 445FS | 447FS
1293 | 447 | 1.1.4.1.2.8 | 6 | Raft Concrete - NTA West side | 2025-11-28T08:00 | 2025-11-29T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 446FS | 448FS
1294 | 448 | 1.1.4.1.2.9 | 6 | Footing & Tie beam Shuttering & Concrete | 2025-11-30T08:00 | 2025-12-01T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 447FS | 475FS
1303 | 449 | 1.1.4.1.3 | 5 | North Side NTA | 2025-10-27T08:00 | 2025-12-06T20:00 | 41.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1306 | 450 | 1.1.4.1.3.1 | 6 | Dressing | 2025-10-27T08:00 | 2025-10-28T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 430SS+4.0d | 451FS
1307 | 451 | 1.1.4.1.3.2 | 6 | PCC | 2025-10-29T08:00 | 2025-10-31T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 450FS | 452FS, 453SS+7.0d
3364 | 452 | 1.1.4.1.3.3 | 6 | Lean Wall Concreting - 4.35 m | 2025-11-01T08:00 | 2025-11-20T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 451FS | 454SS+12.0d
1310 | 453 | 1.1.4.1.3.4 | 6 | Rock Anchoring 17 Nos - Client Scope | 2025-11-07T08:00 | 2025-11-16T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 442SS+5.0d, 451SS+7.0d | 454SS+5.0d
1311 | 454 | 1.1.4.1.3.5 | 6 | Waterproofing - Client Scope | 2025-11-13T08:00 | 2025-11-17T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 453SS+5.0d, 452SS+12.0d | 455FS
1312 | 455 | 1.1.4.1.3.6 | 6 | Raft RF (Incl Footing, SW, RW & Tie Beam) | 2025-11-18T08:00 | 2025-11-29T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 454FS | 456SS+9.0d
1313 | 456 | 1.1.4.1.3.7 | 6 | Raft & Footing - Shuttering | 2025-11-27T08:00 | 2025-12-02T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 455SS+9.0d | 457FS
1314 | 457 | 1.1.4.1.3.8 | 6 | Checking | 2025-12-03T08:00 | 2025-12-03T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 456FS | 458FS
1315 | 458 | 1.1.4.1.3.9 | 6 | Raft Casting | 2025-12-04T08:00 | 2025-12-04T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 457FS | 459FS
1316 | 459 | 1.1.4.1.3.10 | 6 | Footing & Tie beam Shuttering & Concrete | 2025-12-05T08:00 | 2025-12-06T20:00 | 2.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 458FS | 486FS
1317 | 460 | 1.1.4.2 | 4 | Sub Structure - Conventional RCC Slab | 2025-12-02T08:00 | 2026-03-13T20:00 | 98.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1318 | 461 | 1.1.4.2.1 | 5 | Basement 2 - (1st Slab) | 2025-12-02T08:00 | 2026-01-11T20:00 | 41.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2979 | 462 | 1.1.4.2.1.1 | 6 | B2 - South NTA | 2025-12-03T08:00 | 2026-01-02T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2980 | 463 | 1.1.4.2.1.1.1 | 7 | Column & R Wall | 2025-12-03T08:00 | 2025-12-13T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2981 | 464 | 1.1.4.2.1.1.1.1 | 8 | Reinforcement | 2025-12-03T08:00 | 2025-12-08T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 438FS | 465SS+4.0d, 472FS
2982 | 465 | 1.1.4.2.1.1.1.2 | 8 | Shuttering | 2025-12-07T08:00 | 2025-12-11T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 464SS+4.0d | 466SS+4.0d
2983 | 466 | 1.1.4.2.1.1.1.3 | 8 | Column & Shear wall Concrete | 2025-12-11T08:00 | 2025-12-13T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 465SS+4.0d | 468FS
2984 | 467 | 1.1.4.2.1.1.2 | 7 | 1st Slab - South NTA | 2025-12-14T08:00 | 2026-01-02T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
2985 | 468 | 1.1.4.2.1.1.2.1 | 8 | Slab Shuttering | 2025-12-14T08:00 | 2025-12-25T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 466FS | 469SS+8.0d
2986 | 469 | 1.1.4.2.1.1.2.2 | 8 | Reinforcement | 2025-12-22T08:00 | 2025-12-31T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 468SS+8.0d | 470FS
2987 | 470 | 1.1.4.2.1.1.2.3 | 8 | Checking | 2026-01-01T08:00 | 2026-01-01T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 469FS | 471FS
2988 | 471 | 1.1.4.2.1.1.2.4 | 8 | Slab Casting | 2026-01-02T08:00 | 2026-01-02T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 470FS | 498FS
3368 | 472 | 1.1.4.2.1.2 | 6 | RW- South NTA - FDN to 1st Slab | 2025-12-09T08:00 | 2025-12-28T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 464FS | 483SS+7.0d
1319 | 473 | 1.1.4.2.1.3 | 6 | B2 - East NTA | 2025-12-02T08:00 | 2026-01-01T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1320 | 474 | 1.1.4.2.1.3.1 | 7 | Column & R Wall | 2025-12-02T08:00 | 2025-12-12T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1321 | 475 | 1.1.4.2.1.3.1.1 | 8 | Reinforcement | 2025-12-02T08:00 | 2025-12-08T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 448FS | 476SS+4.0d
1322 | 476 | 1.1.4.2.1.3.1.2 | 8 | Shuttering | 2025-12-06T08:00 | 2025-12-10T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 475SS+4.0d | 477SS+4.0d
1323 | 477 | 1.1.4.2.1.3.1.3 | 8 | Column & Shear wall Concrete | 2025-12-10T08:00 | 2025-12-12T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 476SS+4.0d | 479FS
1324 | 478 | 1.1.4.2.1.3.2 | 7 | 1st Slab - East NTA | 2025-12-13T08:00 | 2026-01-01T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1325 | 479 | 1.1.4.2.1.3.2.1 | 8 | Slab Shuttering | 2025-12-13T08:00 | 2025-12-24T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 477FS | 480SS+8.0d
1326 | 480 | 1.1.4.2.1.3.2.2 | 8 | Reinforcement | 2025-12-21T08:00 | 2025-12-30T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 479SS+8.0d | 481FS
1327 | 481 | 1.1.4.2.1.3.2.3 | 8 | Checking | 2025-12-31T08:00 | 2025-12-31T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 480FS | 482FS
1328 | 482 | 1.1.4.2.1.3.2.4 | 8 | Slab Casting | 2026-01-01T08:00 | 2026-01-01T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 481FS | 509FS
3367 | 483 | 1.1.4.2.1.4 | 6 | RW- East NTA - FDN to 1st Slab | 2025-12-16T08:00 | 2026-01-04T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 472SS+7.0d | 494SS+7.0d
1341 | 484 | 1.1.4.2.1.5 | 6 | B2 - North NTA | 2025-12-07T08:00 | 2026-01-06T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1342 | 485 | 1.1.4.2.1.5.1 | 7 | Column & Shear Wall | 2025-12-07T08:00 | 2025-12-17T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1343 | 486 | 1.1.4.2.1.5.1.1 | 8 | Reinforcement | 2025-12-07T08:00 | 2025-12-12T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 459FS | 487SS+4.0d, 494FS
1344 | 487 | 1.1.4.2.1.5.1.2 | 8 | Shuttering | 2025-12-11T08:00 | 2025-12-15T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 486SS+4.0d | 488SS+4.0d
1345 | 488 | 1.1.4.2.1.5.1.3 | 8 | Column & Shear wall Concrete | 2025-12-15T08:00 | 2025-12-17T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 487SS+4.0d | 490FS
1346 | 489 | 1.1.4.2.1.5.2 | 7 | 1st Slab - North NTA | 2025-12-18T08:00 | 2026-01-06T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1347 | 490 | 1.1.4.2.1.5.2.1 | 8 | Slab Shuttering | 2025-12-18T08:00 | 2025-12-29T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 488FS | 491SS+8.0d
1348 | 491 | 1.1.4.2.1.5.2.2 | 8 | Reinforcement | 2025-12-26T08:00 | 2026-01-04T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 490SS+8.0d | 492FS
1349 | 492 | 1.1.4.2.1.5.2.3 | 8 | Checking | 2026-01-05T08:00 | 2026-01-05T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 491FS | 493FS
1350 | 493 | 1.1.4.2.1.5.2.4 | 8 | Slab Casting | 2026-01-06T08:00 | 2026-01-06T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 492FS | 520FS
3366 | 494 | 1.1.4.2.1.6 | 6 | RW- North NTA - FDN to 1st Slab | 2025-12-23T08:00 | 2026-01-11T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 483SS+7.0d, 486FS | 506SS+7.0d
1352 | 495 | 1.1.4.2.2 | 5 | Basement 1- (2nd Slab) | 2026-01-02T08:00 | 2026-02-12T20:00 | 41.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1353 | 496 | 1.1.4.2.2.1 | 6 | B1 - South NTA | 2026-01-03T08:00 | 2026-02-03T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1354 | 497 | 1.1.4.2.2.1.1 | 7 | Column & Shear Wall | 2026-01-03T08:00 | 2026-01-13T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1355 | 498 | 1.1.4.2.2.1.1.1 | 8 | Reinforcement | 2026-01-03T08:00 | 2026-01-08T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 471FS | 499SS+4.0d, 506FS
1356 | 499 | 1.1.4.2.2.1.1.2 | 8 | Shuttering | 2026-01-07T08:00 | 2026-01-11T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 498SS+4.0d | 500SS+4.0d
1357 | 500 | 1.1.4.2.2.1.1.3 | 8 | Column & Shear wall Concrete | 2026-01-11T08:00 | 2026-01-13T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 499SS+4.0d | 502FS
1358 | 501 | 1.1.4.2.2.1.2 | 7 | 2nd Slab - South NTA | 2026-01-14T08:00 | 2026-02-03T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1359 | 502 | 1.1.4.2.2.1.2.1 | 8 | Slab Shuttering | 2026-01-14T08:00 | 2026-01-25T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 500FS | 503SS+8.0d
1360 | 503 | 1.1.4.2.2.1.2.2 | 8 | Reinforcement | 2026-01-22T08:00 | 2026-02-01T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 502SS+8.0d | 504FS
1361 | 504 | 1.1.4.2.2.1.2.3 | 8 | Checking | 2026-02-02T08:00 | 2026-02-02T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 503FS | 505FS
1362 | 505 | 1.1.4.2.2.1.2.4 | 8 | Slab Casting | 2026-02-03T08:00 | 2026-02-03T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 504FS | 532FS
3365 | 506 | 1.1.4.2.2.2 | 6 | RW - South NTA - 1st to 2nd Slab | 2026-01-09T08:00 | 2026-01-29T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 494SS+7.0d, 498FS | 517SS+7.0d
1364 | 507 | 1.1.4.2.2.3 | 6 | B1 - East NTA | 2026-01-02T08:00 | 2026-02-02T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1365 | 508 | 1.1.4.2.2.3.1 | 7 | Column & Shear Wall | 2026-01-02T08:00 | 2026-01-12T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1366 | 509 | 1.1.4.2.2.3.1.1 | 8 | Reinforcement | 2026-01-02T08:00 | 2026-01-08T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 482FS | 510SS+4.0d, 517FS
1367 | 510 | 1.1.4.2.2.3.1.2 | 8 | Shuttering | 2026-01-06T08:00 | 2026-01-10T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 509SS+4.0d | 511SS+4.0d
1369 | 511 | 1.1.4.2.2.3.1.3 | 8 | Column & Shear wall Concrete | 2026-01-10T08:00 | 2026-01-12T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 510SS+4.0d | 513FS
1370 | 512 | 1.1.4.2.2.3.2 | 7 | 2nd Slab - East NTA | 2026-01-13T08:00 | 2026-02-02T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1371 | 513 | 1.1.4.2.2.3.2.1 | 8 | Slab Shuttering | 2026-01-13T08:00 | 2026-01-24T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 511FS | 514SS+8.0d
1372 | 514 | 1.1.4.2.2.3.2.2 | 8 | Reinforcement | 2026-01-21T08:00 | 2026-01-31T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 513SS+8.0d | 515FS
1373 | 515 | 1.1.4.2.2.3.2.3 | 8 | Checking | 2026-02-01T08:00 | 2026-02-01T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 514FS | 516FS
1374 | 516 | 1.1.4.2.2.3.2.4 | 8 | Slab Casting | 2026-02-02T08:00 | 2026-02-02T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 515FS | 543FS
1375 | 517 | 1.1.4.2.2.4 | 6 | RW East NTA - 1st to 2nd Slab | 2026-01-16T08:00 | 2026-02-05T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 506SS+7.0d, 509FS | 528SS+7.0d
1376 | 518 | 1.1.4.2.2.5 | 6 | B1 - North NTA | 2026-01-07T08:00 | 2026-02-07T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1377 | 519 | 1.1.4.2.2.5.1 | 7 | Column & Shear Wall above Footing | 2026-01-07T08:00 | 2026-01-17T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1378 | 520 | 1.1.4.2.2.5.1.1 | 8 | Reinforcement | 2026-01-07T08:00 | 2026-01-12T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 493FS | 521SS+4.0d, 528FS
1379 | 521 | 1.1.4.2.2.5.1.2 | 8 | Shuttering | 2026-01-11T08:00 | 2026-01-15T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 520SS+4.0d | 522SS+4.0d
1381 | 522 | 1.1.4.2.2.5.1.3 | 8 | Column & Shear wall Concrete | 2026-01-15T08:00 | 2026-01-17T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 521SS+4.0d | 524FS
1382 | 523 | 1.1.4.2.2.5.2 | 7 | 2nd Slab - North NTA | 2026-01-18T08:00 | 2026-02-07T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1383 | 524 | 1.1.4.2.2.5.2.1 | 8 | Slab Shuttering | 2026-01-18T08:00 | 2026-01-30T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 522FS | 525SS+8.0d
1384 | 525 | 1.1.4.2.2.5.2.2 | 8 | Reinforcement | 2026-01-27T08:00 | 2026-02-05T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 524SS+8.0d | 526FS
1385 | 526 | 1.1.4.2.2.5.2.3 | 8 | Checking | 2026-02-06T08:00 | 2026-02-06T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 525FS | 527FS
1386 | 527 | 1.1.4.2.2.5.2.4 | 8 | Slab Casting | 2026-02-07T08:00 | 2026-02-07T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 526FS | 554FS
1387 | 528 | 1.1.4.2.2.6 | 6 | RW North NTA - 1st to 2nd Slab | 2026-01-23T08:00 | 2026-02-12T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 520FS, 517SS+7.0d | 540SS+7.0d
1388 | 529 | 1.1.4.2.3 | 5 | Stilt Floor Level - (3rd Slab) | 2026-02-03T08:00 | 2026-03-13T20:00 | 36.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1389 | 530 | 1.1.4.2.3.1 | 6 | Stilt Floor - South NTA | 2026-02-04T08:00 | 2026-03-09T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1390 | 531 | 1.1.4.2.3.1.1 | 7 | Column & Shear Wall above Footing | 2026-02-04T08:00 | 2026-02-14T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1391 | 532 | 1.1.4.2.3.1.1.1 | 8 | Reinforcement | 2026-02-04T08:00 | 2026-02-09T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 505FS | 533SS+4.0d, 540FS
1392 | 533 | 1.1.4.2.3.1.1.2 | 8 | Shuttering | 2026-02-08T08:00 | 2026-02-12T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 532SS+4.0d | 534SS+4.0d
1393 | 534 | 1.1.4.2.3.1.1.3 | 8 | Column & Shear wall Concrete | 2026-02-12T08:00 | 2026-02-14T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 533SS+4.0d | 536FS
1394 | 535 | 1.1.4.2.3.1.2 | 7 | 3rd Slab -South NTA | 2026-02-15T08:00 | 2026-03-09T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1395 | 536 | 1.1.4.2.3.1.2.1 | 8 | Slab Shuttering | 2026-02-15T08:00 | 2026-02-26T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 534FS | 537SS+8.0d
1396 | 537 | 1.1.4.2.3.1.2.2 | 8 | Reinforcement | 2026-02-23T08:00 | 2026-03-07T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 536SS+8.0d | 538FS
1397 | 538 | 1.1.4.2.3.1.2.3 | 8 | Checking | 2026-03-08T08:00 | 2026-03-08T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 537FS | 539FS
1398 | 539 | 1.1.4.2.3.1.2.4 | 8 | Slab Casting | 2026-03-09T08:00 | 2026-03-09T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 538FS | 566FS
1399 | 540 | 1.1.4.2.3.2 | 6 | RW - South NTA - 2nd to 3rd Slab | 2026-02-10T08:00 | 2026-02-24T20:00 | 15.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 528SS+7.0d, 532FS | 551SS+7.0d
1400 | 541 | 1.1.4.2.3.3 | 6 | Stilt Floor - East NTA | 2026-02-03T08:00 | 2026-03-08T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1401 | 542 | 1.1.4.2.3.3.1 | 7 | Column & Shear Wall | 2026-02-03T08:00 | 2026-02-13T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1402 | 543 | 1.1.4.2.3.3.1.1 | 8 | Reinforcement | 2026-02-03T08:00 | 2026-02-09T20:00 | 7.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 516FS | 544SS+4.0d, 551FS
1403 | 544 | 1.1.4.2.3.3.1.2 | 8 | Shuttering | 2026-02-07T08:00 | 2026-02-11T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 543SS+4.0d | 545SS+4.0d
1405 | 545 | 1.1.4.2.3.3.1.3 | 8 | Column & Shear wall Concrete | 2026-02-11T08:00 | 2026-02-13T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 544SS+4.0d | 547FS
1406 | 546 | 1.1.4.2.3.3.2 | 7 | 3rd Slab - East NTA | 2026-02-14T08:00 | 2026-03-08T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1407 | 547 | 1.1.4.2.3.3.2.1 | 8 | Slab Shuttering | 2026-02-14T08:00 | 2026-02-25T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 545FS | 548SS+8.0d
1408 | 548 | 1.1.4.2.3.3.2.2 | 8 | Reinforcement | 2026-02-22T08:00 | 2026-03-06T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 547SS+8.0d | 549FS
1409 | 549 | 1.1.4.2.3.3.2.3 | 8 | Checking | 2026-03-07T08:00 | 2026-03-07T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 548FS | 550FS
1410 | 550 | 1.1.4.2.3.3.2.4 | 8 | Slab Casting | 2026-03-08T08:00 | 2026-03-08T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 549FS | 566FS
1411 | 551 | 1.1.4.2.3.4 | 6 | RW - East NTA - 2nd to 3rd Slab | 2026-02-17T08:00 | 2026-03-11T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 543FS, 540SS+7.0d | 561SS+7.0d
1412 | 552 | 1.1.4.2.3.5 | 6 | Stilt Floor - North NTA | 2026-02-08T08:00 | 2026-03-13T20:00 | 31.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1413 | 553 | 1.1.4.2.3.5.1 | 7 | Column & Shear Wall | 2026-02-08T08:00 | 2026-02-18T20:00 | 11.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1414 | 554 | 1.1.4.2.3.5.1.1 | 8 | Reinforcement | 2026-02-08T08:00 | 2026-02-13T20:00 | 6.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 527FS | 555SS+4.0d, 562FS
1415 | 555 | 1.1.4.2.3.5.1.2 | 8 | Shuttering | 2026-02-12T08:00 | 2026-02-16T20:00 | 5.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 554SS+4.0d | 556SS+4.0d
1417 | 556 | 1.1.4.2.3.5.1.3 | 8 | Column & Shear wall Concrete | 2026-02-16T08:00 | 2026-02-18T20:00 | 3.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 555SS+4.0d | 558FS
1418 | 557 | 1.1.4.2.3.5.2 | 7 | 3rd Slab - North NTA | 2026-02-19T08:00 | 2026-03-13T20:00 | 20.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
1419 | 558 | 1.1.4.2.3.5.2.1 | 8 | Slab Shuttering | 2026-02-19T08:00 | 2026-03-02T20:00 | 12.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 556FS | 559SS+8.0d
1420 | 559 | 1.1.4.2.3.5.2.2 | 8 | Reinforcement | 2026-02-27T08:00 | 2026-03-11T20:00 | 10.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 558SS+8.0d | 560FS
1421 | 560 | 1.1.4.2.3.5.2.3 | 8 | Checking | 2026-03-12T08:00 | 2026-03-12T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 559FS | 561FS
1422 | 561 | 1.1.4.2.3.5.2.4 | 8 | Slab Casting | 2026-03-13T08:00 | 2026-03-13T20:00 | 1.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 560FS, 551SS+7.0d | 564FS
1423 | 562 | 1.1.4.2.3.6 | 6 | RW - North NTA - 2nd to 3rd Slab | 2026-02-14T08:00 | 2026-03-08T20:00 | 20.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 554FS | 567FS
1457 | 563 | 1.1.4.3 | 4 | Post Pour - NTA | 2026-03-14T08:00 | 2026-06-30T20:00 | 105.0d | 0.0 |  |  |  |  | False | True | False | AS_SOON_AS_POSSIBLE
3171 | 564 | 1.1.4.3.1 | 5 | Basement 2 -1st slab | 2026-03-14T08:00 | 2026-04-19T20:00 | 35.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 561FS | 565FS, 567FS
3170 | 565 | 1.1.4.3.2 | 5 | Basement 1 - 2nd slab | 2026-04-20T08:00 | 2026-05-25T20:00 | 35.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 564FS | 566FS, 567FS
3169 | 566 | 1.1.4.3.3 | 5 | Stilt Level - 3rd slab | 2026-05-26T08:00 | 2026-06-30T20:00 | 35.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 565FS, 550FS, 539FS | 567FS
1458 | 567 | 1.1.5 | 3 | Handover | 2026-07-01T08:00 | 2026-07-25T20:00 | 25.0d | 0.0 |  |  |  |  | False | False | False | AS_SOON_AS_POSSIBLE |  | 566FS, 564FS, 565FS, 562FS

## Assignments
Task ID | Task Name | Resource ID | Resource Name | Start | Finish | Units | Work | Actual Work | Remaining Work | Cost | Delay | Notes
442 | Rock Anchoring 9 Nos - Client Scope |  |  | 2025-11-02T08:00 | 2025-11-11T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
443 | Waterproofing - Client Scope |  |  | 2025-11-07T08:00 | 2025-11-11T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
444 | Raft RF (Incl Footing, SW, RW & Tie Beam) |  |  | 2025-11-10T08:00 | 2025-11-21T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
445 | Shuttering |  |  | 2025-11-19T08:00 | 2025-11-26T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
446 | Checking |  |  | 2025-11-27T08:00 | 2025-11-27T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
447 | Raft Concrete - NTA West side |  |  | 2025-11-28T08:00 | 2025-11-29T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
448 | Footing & Tie beam Shuttering & Concrete |  |  | 2025-11-30T08:00 | 2025-12-01T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
450 | Dressing |  |  | 2025-10-27T08:00 | 2025-10-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
451 | PCC |  |  | 2025-10-29T08:00 | 2025-10-31T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
453 | Rock Anchoring 17 Nos - Client Scope |  |  | 2025-11-07T08:00 | 2025-11-16T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
454 | Waterproofing - Client Scope |  |  | 2025-11-13T08:00 | 2025-11-17T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
455 | Raft RF (Incl Footing, SW, RW & Tie Beam) |  |  | 2025-11-18T08:00 | 2025-11-29T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
456 | Raft & Footing - Shuttering |  |  | 2025-11-27T08:00 | 2025-12-02T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
457 | Checking |  |  | 2025-12-03T08:00 | 2025-12-03T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
458 | Raft Casting |  |  | 2025-12-04T08:00 | 2025-12-04T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
459 | Footing & Tie beam Shuttering & Concrete |  |  | 2025-12-05T08:00 | 2025-12-06T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
475 | Reinforcement |  |  | 2025-12-02T08:00 | 2025-12-08T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
476 | Shuttering |  |  | 2025-12-06T08:00 | 2025-12-10T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
477 | Column & Shear wall Concrete |  |  | 2025-12-10T08:00 | 2025-12-12T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
479 | Slab Shuttering |  |  | 2025-12-13T08:00 | 2025-12-24T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
480 | Reinforcement |  |  | 2025-12-21T08:00 | 2025-12-30T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
481 | Checking |  |  | 2025-12-31T08:00 | 2025-12-31T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
482 | Slab Casting |  |  | 2026-01-01T08:00 | 2026-01-01T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
486 | Reinforcement |  |  | 2025-12-07T08:00 | 2025-12-12T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
487 | Shuttering |  |  | 2025-12-11T08:00 | 2025-12-15T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
488 | Column & Shear wall Concrete |  |  | 2025-12-15T08:00 | 2025-12-17T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
490 | Slab Shuttering |  |  | 2025-12-18T08:00 | 2025-12-29T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
491 | Reinforcement |  |  | 2025-12-26T08:00 | 2026-01-04T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
492 | Checking |  |  | 2026-01-05T08:00 | 2026-01-05T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
493 | Slab Casting |  |  | 2026-01-06T08:00 | 2026-01-06T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
498 | Reinforcement |  |  | 2026-01-03T08:00 | 2026-01-08T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
499 | Shuttering |  |  | 2026-01-07T08:00 | 2026-01-11T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
500 | Column & Shear wall Concrete |  |  | 2026-01-11T08:00 | 2026-01-13T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
502 | Slab Shuttering |  |  | 2026-01-14T08:00 | 2026-01-25T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
503 | Reinforcement |  |  | 2026-01-22T08:00 | 2026-02-01T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
504 | Checking |  |  | 2026-02-02T08:00 | 2026-02-02T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
505 | Slab Casting |  |  | 2026-02-03T08:00 | 2026-02-03T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
509 | Reinforcement |  |  | 2026-01-02T08:00 | 2026-01-08T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
510 | Shuttering |  |  | 2026-01-06T08:00 | 2026-01-10T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
511 | Column & Shear wall Concrete |  |  | 2026-01-10T08:00 | 2026-01-12T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
513 | Slab Shuttering |  |  | 2026-01-13T08:00 | 2026-01-24T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
514 | Reinforcement |  |  | 2026-01-21T08:00 | 2026-01-31T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
515 | Checking |  |  | 2026-02-01T08:00 | 2026-02-01T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
516 | Slab Casting |  |  | 2026-02-02T08:00 | 2026-02-02T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
517 | RW East NTA - 1st to 2nd Slab |  |  | 2026-01-16T08:00 | 2026-02-05T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
520 | Reinforcement |  |  | 2026-01-07T08:00 | 2026-01-12T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
521 | Shuttering |  |  | 2026-01-11T08:00 | 2026-01-15T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
522 | Column & Shear wall Concrete |  |  | 2026-01-15T08:00 | 2026-01-17T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
524 | Slab Shuttering |  |  | 2026-01-18T08:00 | 2026-01-30T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
525 | Reinforcement |  |  | 2026-01-27T08:00 | 2026-02-05T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
526 | Checking |  |  | 2026-02-06T08:00 | 2026-02-06T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
527 | Slab Casting |  |  | 2026-02-07T08:00 | 2026-02-07T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
528 | RW North NTA - 1st to 2nd Slab |  |  | 2026-01-23T08:00 | 2026-02-12T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
532 | Reinforcement |  |  | 2026-02-04T08:00 | 2026-02-09T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
533 | Shuttering |  |  | 2026-02-08T08:00 | 2026-02-12T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
534 | Column & Shear wall Concrete |  |  | 2026-02-12T08:00 | 2026-02-14T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
536 | Slab Shuttering |  |  | 2026-02-15T08:00 | 2026-02-26T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
537 | Reinforcement |  |  | 2026-02-23T08:00 | 2026-03-07T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
538 | Checking |  |  | 2026-03-08T08:00 | 2026-03-08T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
539 | Slab Casting |  |  | 2026-03-09T08:00 | 2026-03-09T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
540 | RW - South NTA - 2nd to 3rd Slab |  |  | 2026-02-10T08:00 | 2026-02-24T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
543 | Reinforcement |  |  | 2026-02-03T08:00 | 2026-02-09T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
544 | Shuttering |  |  | 2026-02-07T08:00 | 2026-02-11T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
545 | Column & Shear wall Concrete |  |  | 2026-02-11T08:00 | 2026-02-13T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
547 | Slab Shuttering |  |  | 2026-02-14T08:00 | 2026-02-25T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
548 | Reinforcement |  |  | 2026-02-22T08:00 | 2026-03-06T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
549 | Checking |  |  | 2026-03-07T08:00 | 2026-03-07T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
550 | Slab Casting |  |  | 2026-03-08T08:00 | 2026-03-08T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
551 | RW - East NTA - 2nd to 3rd Slab |  |  | 2026-02-17T08:00 | 2026-03-11T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
554 | Reinforcement |  |  | 2026-02-08T08:00 | 2026-02-13T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
555 | Shuttering |  |  | 2026-02-12T08:00 | 2026-02-16T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
556 | Column & Shear wall Concrete |  |  | 2026-02-16T08:00 | 2026-02-18T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
558 | Slab Shuttering |  |  | 2026-02-19T08:00 | 2026-03-02T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
559 | Reinforcement |  |  | 2026-02-27T08:00 | 2026-03-11T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
560 | Checking |  |  | 2026-03-12T08:00 | 2026-03-12T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
561 | Slab Casting |  |  | 2026-03-13T08:00 | 2026-03-13T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
562 | RW - North NTA - 2nd to 3rd Slab |  |  | 2026-02-14T08:00 | 2026-03-08T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
567 | Handover |  |  | 2026-07-01T08:00 | 2026-07-25T20:00 | 100.0 | 275.0h | 0.0h | 275.0h | 0.0 | 0.0h
432 | Rock Anchoring 28 Nos - Client Scope |  |  | 2025-10-27T08:00 | 2025-11-05T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
433 | Waterproofing - Client Scope |  |  | 2025-11-04T08:00 | 2025-11-08T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
434 | Raft RF (Incl Footing, SW, RW & Tie Beam) |  |  | 2025-11-11T08:00 | 2025-11-22T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
435 | Shuttering |  |  | 2025-11-20T08:00 | 2025-11-27T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
436 | Checking |  |  | 2025-11-28T08:00 | 2025-11-28T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
437 | Raft Concrete - South side |  |  | 2025-11-29T08:00 | 2025-11-30T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
438 | Footing & Tie beam Shuttering & Concrete |  |  | 2025-12-01T08:00 | 2025-12-02T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
4 | Letter of Acceptance |  |  | 2025-10-18T08:00 | 2025-10-18T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
5 | Mobilization Period |  |  | 2025-10-18T08:00 | 2025-11-20T20:00 | 100.0 | 330.0h | 0.0h | 330.0h | 0.0 | 0.0h
6 | Excavation Completion & Handing Over of Site |  |  | 2025-10-18T08:00 | 2025-10-18T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
12 | Dressing |  |  | 2025-10-19T08:00 | 2025-10-24T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
13 | PCC |  |  | 2025-10-25T08:00 | 2025-10-26T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
14 | Waterproofing Work - Client scope |  |  | 2025-10-30T08:00 | 2025-11-03T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
16 | Raft RF (Incl Footing, SW, RW & Tie Beam) |  |  | 2025-11-11T08:00 | 2025-11-25T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
17 | Shuttering |  |  | 2025-11-19T08:00 | 2025-11-27T20:00 | 100.0 | 99.0h | 0.0h | 99.0h | 0.0 | 0.0h
18 | Checking |  |  | 2025-11-28T08:00 | 2025-11-28T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
19 | Raft Concrete |  |  | 2025-11-29T08:00 | 2025-11-30T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
21 | Shuttering for Footing |  |  | 2025-12-01T08:00 | 2025-12-01T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
22 | Footing Concrete |  |  | 2025-12-02T08:00 | 2025-12-02T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
24 | Dressing |  |  | 2025-10-25T08:00 | 2025-10-26T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
25 | PCC |  |  | 2025-10-27T08:00 | 2025-10-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
26 | Waterproofing Work - Client scope |  |  | 2025-11-01T08:00 | 2025-11-05T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
28 | Raft RF (Incl Footing, SW, RW & Tie Beam) |  |  | 2025-11-04T08:00 | 2025-11-18T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
29 | Shuttering |  |  | 2025-11-12T08:00 | 2025-11-20T20:00 | 100.0 | 99.0h | 0.0h | 99.0h | 0.0 | 0.0h
30 | Checking |  |  | 2025-11-21T08:00 | 2025-11-21T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
31 | Raft Concrete |  |  | 2025-11-22T08:00 | 2025-11-23T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
33 | Shuttering for Footing |  |  | 2025-11-24T08:00 | 2025-11-24T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
34 | Footing Concrete |  |  | 2025-11-25T08:00 | 2025-11-25T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
36 | Dressing |  |  | 2025-10-27T08:00 | 2025-10-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
37 | PCC |  |  | 2025-10-29T08:00 | 2025-10-30T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
39 | Waterproofing Work - Client Scope |  |  | 2025-11-04T08:00 | 2025-11-08T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
41 | Raft RF (Incl Footing, SW, RW & Tie Beam) |  |  | 2025-11-07T08:00 | 2025-11-21T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
42 | Shuttering |  |  | 2025-11-15T08:00 | 2025-11-23T20:00 | 100.0 | 99.0h | 0.0h | 99.0h | 0.0 | 0.0h
43 | Checking |  |  | 2025-11-24T08:00 | 2025-11-24T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
44 | Raft Concrete |  |  | 2025-11-25T08:00 | 2025-11-26T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
46 | Shuttering |  |  | 2025-11-27T08:00 | 2025-11-27T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
47 | Footing Concrete |  |  | 2025-11-28T08:00 | 2025-11-28T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
52 | Reinforcement |  |  | 2025-12-03T08:00 | 2025-12-10T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
53 | Shuttering |  |  | 2025-12-07T08:00 | 2025-12-12T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
54 | Checking |  |  | 2025-12-13T08:00 | 2025-12-13T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
55 | Column & Shear wall Concrete |  |  | 2025-12-14T08:00 | 2025-12-15T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
57 | Slab Shuttering |  |  | 2025-12-16T08:00 | 2025-12-30T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
58 | Reinforcement |  |  | 2025-12-23T08:00 | 2026-01-01T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
59 | Checking |  |  | 2026-01-02T08:00 | 2026-01-02T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
60 | Slab Casting |  |  | 2026-01-03T08:00 | 2026-01-03T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
63 | Reinforcement |  |  | 2025-11-26T08:00 | 2025-12-03T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
64 | Shuttering |  |  | 2025-11-30T08:00 | 2025-12-05T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
65 | Checking |  |  | 2025-12-06T08:00 | 2025-12-06T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
66 | Column & Shear wall Concrete |  |  | 2025-12-07T08:00 | 2025-12-08T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
68 | Slab Shuttering |  |  | 2025-12-09T08:00 | 2025-12-23T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
69 | Reinforcement |  |  | 2025-12-16T08:00 | 2025-12-25T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
70 | Checking |  |  | 2025-12-26T08:00 | 2025-12-26T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
71 | Slab Casting |  |  | 2025-12-27T08:00 | 2025-12-27T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
74 | Reinforcement |  |  | 2025-11-29T08:00 | 2025-12-06T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
75 | Shuttering |  |  | 2025-12-03T08:00 | 2025-12-08T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
76 | Checking |  |  | 2025-12-09T08:00 | 2025-12-09T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
77 | Column & Shear wall Concrete |  |  | 2025-12-10T08:00 | 2025-12-11T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
79 | Slab Shuttering |  |  | 2025-12-12T08:00 | 2025-12-26T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
80 | Reinforcement |  |  | 2025-12-19T08:00 | 2025-12-28T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
81 | Checking |  |  | 2025-12-29T08:00 | 2025-12-29T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
82 | Slab Casting |  |  | 2025-12-30T08:00 | 2025-12-30T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
86 | Reinforcement |  |  | 2026-01-04T08:00 | 2026-01-11T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
87 | Shuttering |  |  | 2026-01-07T08:00 | 2026-01-12T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
88 | Checking |  |  | 2026-01-13T08:00 | 2026-01-13T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
89 | Column & Shear wall Concrete |  |  | 2026-01-14T08:00 | 2026-01-15T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
91 | Slab Shuttering |  |  | 2026-01-16T08:00 | 2026-01-31T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
92 | Reinforcement |  |  | 2026-01-23T08:00 | 2026-02-02T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
93 | Checking |  |  | 2026-02-03T08:00 | 2026-02-03T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
94 | Slab Casting |  |  | 2026-02-04T08:00 | 2026-02-04T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
97 | Reinforcement |  |  | 2025-12-28T08:00 | 2026-01-04T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
98 | Shuttering |  |  | 2025-12-31T08:00 | 2026-01-05T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
99 | Checking |  |  | 2026-01-06T08:00 | 2026-01-06T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
100 | Column & Shear wall Concrete |  |  | 2026-01-07T08:00 | 2026-01-08T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
102 | Slab Shuttering |  |  | 2026-01-09T08:00 | 2026-01-23T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
103 | Reinforcement |  |  | 2026-01-16T08:00 | 2026-01-25T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
104 | Checking |  |  | 2026-01-27T08:00 | 2026-01-27T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
105 | Slab Casting |  |  | 2026-01-28T08:00 | 2026-01-28T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
108 | Reinforcement |  |  | 2025-12-31T08:00 | 2026-01-07T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
109 | Shuttering |  |  | 2026-01-03T08:00 | 2026-01-08T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
110 | Checking |  |  | 2026-01-09T08:00 | 2026-01-09T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
111 | Column & Shear wall Concrete |  |  | 2026-01-10T08:00 | 2026-01-11T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
113 | Slab Shuttering |  |  | 2026-01-12T08:00 | 2026-01-27T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
114 | Reinforcement |  |  | 2026-01-19T08:00 | 2026-01-29T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
115 | Checking |  |  | 2026-01-30T08:00 | 2026-01-30T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
116 | Slab Casting |  |  | 2026-01-31T08:00 | 2026-01-31T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
120 | Reinforcement |  |  | 2026-02-05T08:00 | 2026-02-12T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
121 | Shuttering |  |  | 2026-02-08T08:00 | 2026-02-13T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
122 | Checking |  |  | 2026-02-14T08:00 | 2026-02-14T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
123 | Column & Shear wall Concrete |  |  | 2026-02-15T08:00 | 2026-02-16T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
125 | Slab Shuttering |  |  | 2026-02-17T08:00 | 2026-03-06T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
126 | Reinforcement |  |  | 2026-02-24T08:00 | 2026-03-08T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
127 | Checking |  |  | 2026-03-09T08:00 | 2026-03-09T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
128 | Slab Casting |  |  | 2026-03-10T08:00 | 2026-03-10T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
131 | Reinforcement |  |  | 2026-01-29T08:00 | 2026-02-05T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
132 | Shuttering |  |  | 2026-02-01T08:00 | 2026-02-06T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
133 | Checking |  |  | 2026-02-07T08:00 | 2026-02-07T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
134 | Column & Shear wall Concrete |  |  | 2026-02-08T08:00 | 2026-02-09T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
136 | Slab Shuttering |  |  | 2026-02-10T08:00 | 2026-02-24T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
137 | Reinforcement |  |  | 2026-02-17T08:00 | 2026-02-26T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
138 | Checking |  |  | 2026-02-27T08:00 | 2026-02-27T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
139 | Slab Casting |  |  | 2026-02-28T08:00 | 2026-02-28T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
142 | Reinforcement |  |  | 2026-02-01T08:00 | 2026-02-08T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
143 | Shuttering |  |  | 2026-02-04T08:00 | 2026-02-09T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
144 | Checking |  |  | 2026-02-10T08:00 | 2026-02-10T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
145 | Column & Shear wall Concrete |  |  | 2026-02-11T08:00 | 2026-02-12T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
147 | Slab Shuttering |  |  | 2026-02-13T08:00 | 2026-02-27T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
148 | Reinforcement |  |  | 2026-02-20T08:00 | 2026-03-01T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
149 | Checking |  |  | 2026-03-02T08:00 | 2026-03-02T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
150 | Slab Casting |  |  | 2026-03-06T08:00 | 2026-03-06T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
154 | Reinforcement |  |  | 2026-03-11T08:00 | 2026-03-18T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
155 | Shuttering |  |  | 2026-03-14T08:00 | 2026-03-19T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
156 | Checking |  |  | 2026-03-20T08:00 | 2026-03-20T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
157 | Column & Shear wall Concrete |  |  | 2026-03-23T08:00 | 2026-03-24T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
159 | Slab Shuttering |  |  | 2026-03-25T08:00 | 2026-04-08T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
160 | Reinforcement |  |  | 2026-04-01T08:00 | 2026-04-10T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
161 | Checking |  |  | 2026-04-11T08:00 | 2026-04-11T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
162 | Slab Casting |  |  | 2026-04-12T08:00 | 2026-04-12T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
165 | Reinforcement |  |  | 2026-03-01T08:00 | 2026-03-11T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
166 | Shuttering |  |  | 2026-03-07T08:00 | 2026-03-12T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
167 | Checking |  |  | 2026-03-13T08:00 | 2026-03-13T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
168 | Column & Shear wall Concrete |  |  | 2026-03-14T08:00 | 2026-03-15T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
170 | Slab Shuttering |  |  | 2026-03-16T08:00 | 2026-04-01T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
171 | Reinforcement |  |  | 2026-03-25T08:00 | 2026-04-03T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
172 | Checking |  |  | 2026-04-04T08:00 | 2026-04-04T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
173 | Slab Casting |  |  | 2026-04-05T08:00 | 2026-04-05T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
176 | Reinforcement |  |  | 2026-03-07T08:00 | 2026-03-14T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
177 | Shuttering |  |  | 2026-03-10T08:00 | 2026-03-15T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
178 | Checking |  |  | 2026-03-16T08:00 | 2026-03-16T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
179 | Column & Shear wall Concrete |  |  | 2026-03-17T08:00 | 2026-03-18T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
181 | Slab Shuttering |  |  | 2026-03-19T08:00 | 2026-04-04T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
182 | Reinforcement |  |  | 2026-03-28T08:00 | 2026-04-06T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
183 | Checking |  |  | 2026-04-07T08:00 | 2026-04-07T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
184 | Slab Casting |  |  | 2026-04-08T08:00 | 2026-04-08T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
185 | Ground Floor Grade Slab / Trimix |  |  | 2026-04-13T08:00 | 2026-05-13T20:00 | 100.0 | 330.0h | 0.0h | 330.0h | 0.0 | 0.0h
186 | Receipt of Aluform Material |  |  | 2026-03-27T08:00 | 2026-04-10T20:00 | 100.0 | 165.0h | 0.0h | 165.0h | 0.0 | 0.0h
231 | Vertical Reinforcement Work |  |  | 2026-08-20T08:00 | 2026-08-21T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
232 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-08-21T08:00 | 2026-08-24T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
233 | Slab & Beam Reinforcement Work |  |  | 2026-08-25T08:00 | 2026-08-28T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
234 | Electrical Conduiting & Checking |  |  | 2026-08-29T08:00 | 2026-08-30T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
235 | Slab Casting |  |  | 2026-08-31T08:00 | 2026-08-31T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
237 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-09-01T08:00 | 2026-09-01T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
238 | Vertical Reinforcement Work |  |  | 2026-09-01T08:00 | 2026-09-02T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
239 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-09-02T08:00 | 2026-09-05T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
240 | Slab & Beam Reinforcement Work |  |  | 2026-09-06T08:00 | 2026-09-09T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
241 | Electrical Conduiting & Checking |  |  | 2026-09-10T08:00 | 2026-09-11T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
378 | Vertical Reinforcement Work |  |  | 2027-06-15T08:00 | 2027-06-16T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
379 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-06-16T08:00 | 2027-06-19T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
380 | Slab & Beam Reinforcement Work |  |  | 2027-06-20T08:00 | 2027-06-23T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
381 | Electrical Conduiting & Checking |  |  | 2027-06-24T08:00 | 2027-06-25T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
382 | Slab Casting |  |  | 2027-06-26T08:00 | 2027-06-26T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
391 | Parapet Wall |  |  | 2027-07-09T08:00 | 2027-08-07T20:00 | 100.0 | 330.0h | 0.0h | 330.0h | 0.0 | 0.0h
392 | LMR Bottom Slab |  |  | 2027-07-14T08:00 | 2027-08-07T20:00 | 100.0 | 275.0h | 0.0h | 275.0h | 0.0 | 0.0h
393 | LMR Top Slab |  |  | 2027-08-10T08:00 | 2027-09-07T20:00 | 100.0 | 308.0h | 0.0h | 308.0h | 0.0 | 0.0h
394 | Elevation Pargola Work |  |  | 2027-08-08T08:00 | 2027-09-23T20:00 | 100.0 | 495.0h | 0.0h | 495.0h | 0.0 | 0.0h
426 | Handover |  |  | 2027-11-21T08:00 | 2027-12-10T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
464 | Reinforcement |  |  | 2025-12-03T08:00 | 2025-12-08T20:00 | 100.0 | 66.0h | 0.0h | 66.0h | 0.0 | 0.0h
465 | Shuttering |  |  | 2025-12-07T08:00 | 2025-12-11T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
466 | Column & Shear wall Concrete |  |  | 2025-12-11T08:00 | 2025-12-13T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
468 | Slab Shuttering |  |  | 2025-12-14T08:00 | 2025-12-25T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
469 | Reinforcement |  |  | 2025-12-22T08:00 | 2025-12-31T20:00 | 100.0 | 110.0h | 0.0h | 110.0h | 0.0 | 0.0h
470 | Checking |  |  | 2026-01-01T08:00 | 2026-01-01T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
471 | Slab Casting |  |  | 2026-01-02T08:00 | 2026-01-02T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
413 | 18th floor |  |  | 2027-03-18T08:00 | 2027-04-01T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
412 | 17th Refuge floor |  |  | 2027-03-03T08:00 | 2027-03-16T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
411 | 16th floor |  |  | 2027-02-18T08:00 | 2027-03-01T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
410 | 15th floor |  |  | 2027-02-05T08:00 | 2027-02-16T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
406 | 11th floor |  |  | 2026-12-11T08:00 | 2026-12-22T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
405 | 10th floor |  |  | 2026-11-28T08:00 | 2026-12-09T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
404 | 9th floor |  |  | 2026-11-15T08:00 | 2026-11-26T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
403 | 8th floor |  |  | 2026-10-30T08:00 | 2026-11-13T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
402 | 7th Refuge floor |  |  | 2026-10-15T08:00 | 2026-10-28T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
401 | 6th floor |  |  | 2026-10-01T08:00 | 2026-10-12T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
400 | 5th floor |  |  | 2026-09-18T08:00 | 2026-09-29T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
399 | 4th floor |  |  | 2026-09-02T08:00 | 2026-09-13T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
398 | 3rd floor |  |  | 2026-08-20T08:00 | 2026-08-31T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
397 | 2nd floor |  |  | 2026-08-01T08:00 | 2026-08-12T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
396 | 1st Floor |  |  | 2026-07-18T08:00 | 2026-07-29T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
407 | 12th Refuge floor |  |  | 2026-12-24T08:00 | 2027-01-04T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
408 | 13th floor |  |  | 2027-01-06T08:00 | 2027-01-17T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
409 | 14th floor |  |  | 2027-01-22T08:00 | 2027-02-03T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
424 | 29th floor |  |  | 2027-08-12T08:00 | 2027-08-23T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
423 | 28th floor |  |  | 2027-07-29T08:00 | 2027-08-09T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
422 | 27th floor |  |  | 2027-07-16T08:00 | 2027-07-27T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
421 | 26th Refuge floor |  |  | 2027-07-03T08:00 | 2027-07-14T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
420 | 25th floor |  |  | 2027-06-20T08:00 | 2027-07-01T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
419 | 24th floor |  |  | 2027-06-07T08:00 | 2027-06-18T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
418 | 23rd floor |  |  | 2027-05-26T08:00 | 2027-06-06T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
417 | 22nd floor |  |  | 2027-05-13T08:00 | 2027-05-25T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
416 | 21st Refuge floor |  |  | 2027-04-29T08:00 | 2027-05-11T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
415 | 20th floor |  |  | 2027-04-16T08:00 | 2027-04-27T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
414 | 19th floor |  |  | 2027-04-03T08:00 | 2027-04-14T20:00 | 100.0 | 132.0h | 0.0h | 132.0h | 0.0 | 0.0h
425 | External Post Pour work |  |  | 2027-08-16T08:00 | 2027-11-19T20:00 | 100.0 | 990.0h | 0.0h | 990.0h | 0.0 | 0.0h
566 | Stilt Level - 3rd slab |  |  | 2026-05-26T08:00 | 2026-06-30T20:00 | 100.0 | 385.0h | 0.0h | 385.0h | 0.0 | 0.0h
565 | Basement 1 - 2nd slab |  |  | 2026-04-20T08:00 | 2026-05-25T20:00 | 100.0 | 385.0h | 0.0h | 385.0h | 0.0 | 0.0h
564 | Basement 2 -1st slab |  |  | 2026-03-14T08:00 | 2026-04-19T20:00 | 100.0 | 385.0h | 0.0h | 385.0h | 0.0 | 0.0h
189 | Vertical Reinforcement Work |  |  | 2026-04-11T08:00 | 2026-04-18T20:00 | 100.0 | 88.0h | 0.0h | 88.0h | 0.0 | 0.0h
190 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-04-19T08:00 | 2026-05-07T20:00 | 100.0 | 198.0h | 0.0h | 198.0h | 0.0 | 0.0h
191 | Slab & Beam Reinforcement Work |  |  | 2026-05-08T08:00 | 2026-05-21T20:00 | 100.0 | 154.0h | 0.0h | 154.0h | 0.0 | 0.0h
192 | Electrical Conduiting & Checking |  |  | 2026-05-22T08:00 | 2026-05-24T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
193 | Slab Casting |  |  | 2026-05-25T08:00 | 2026-05-25T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
196 | Vertical Reinforcement Work |  |  | 2026-05-28T08:00 | 2026-06-01T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
197 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-06-02T08:00 | 2026-06-05T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
198 | Slab & Beam Reinforcement Work |  |  | 2026-06-06T08:00 | 2026-06-12T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
199 | Electrical Conduiting & Checking |  |  | 2026-06-13T08:00 | 2026-06-14T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
200 | Slab Casting |  |  | 2026-06-15T08:00 | 2026-06-15T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
230 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-08-20T08:00 | 2026-08-20T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
195 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-05-26T08:00 | 2026-05-26T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
220 | Electrical Conduiting & Checking |  |  | 2026-07-27T08:00 | 2026-07-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
221 | Slab Casting |  |  | 2026-07-29T08:00 | 2026-07-29T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
223 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-07-30T08:00 | 2026-07-30T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
224 | Vertical Reinforcement Work |  |  | 2026-07-31T08:00 | 2026-08-04T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
225 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-08-05T08:00 | 2026-08-08T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
226 | Slab & Beam Reinforcement Work |  |  | 2026-08-09T08:00 | 2026-08-16T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
227 | Electrical Conduiting & Checking |  |  | 2026-08-17T08:00 | 2026-08-18T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
228 | Slab Casting |  |  | 2026-08-19T08:00 | 2026-08-19T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
203 | Vertical Reinforcement Work |  |  | 2026-06-17T08:00 | 2026-06-19T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
204 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-06-20T08:00 | 2026-06-23T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
205 | Slab & Beam Reinforcement Work |  |  | 2026-06-24T08:00 | 2026-06-28T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
206 | Electrical Conduiting & Checking |  |  | 2026-06-29T08:00 | 2026-06-30T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
207 | Slab Casting |  |  | 2026-07-01T08:00 | 2026-07-01T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
209 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-07-02T08:00 | 2026-07-02T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
210 | Vertical Reinforcement Work |  |  | 2026-07-03T08:00 | 2026-07-05T20:00 | 100.0 | 33.0h | 0.0h | 33.0h | 0.0 | 0.0h
211 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-07-06T08:00 | 2026-07-09T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
212 | Slab & Beam Reinforcement Work |  |  | 2026-07-10T08:00 | 2026-07-14T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
213 | Electrical Conduiting & Checking |  |  | 2026-07-15T08:00 | 2026-07-16T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
214 | Slab Casting |  |  | 2026-07-17T08:00 | 2026-07-17T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
216 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-07-18T08:00 | 2026-07-18T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
217 | Vertical Reinforcement Work |  |  | 2026-07-18T08:00 | 2026-07-19T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
218 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-07-19T08:00 | 2026-07-22T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
219 | Slab & Beam Reinforcement Work |  |  | 2026-07-23T08:00 | 2026-07-26T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
202 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-06-16T08:00 | 2026-06-16T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
244 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-09-13T08:00 | 2026-09-13T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
245 | Vertical Reinforcement Work |  |  | 2026-09-13T08:00 | 2026-09-15T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
246 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-09-15T08:00 | 2026-09-19T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
247 | Slab & Beam Reinforcement Work |  |  | 2026-09-20T08:00 | 2026-09-23T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
248 | Electrical Conduiting & Checking |  |  | 2026-09-24T08:00 | 2026-09-25T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
249 | Slab Casting |  |  | 2026-09-26T08:00 | 2026-09-26T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
251 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-09-27T08:00 | 2026-09-27T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
252 | Vertical Reinforcement Work |  |  | 2026-09-27T08:00 | 2026-09-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
253 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-09-28T08:00 | 2026-10-01T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
254 | Slab & Beam Reinforcement Work |  |  | 2026-10-02T08:00 | 2026-10-05T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
255 | Electrical Conduiting & Checking |  |  | 2026-10-06T08:00 | 2026-10-07T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
289 | Slab & Beam Reinforcement Work |  |  | 2026-12-14T08:00 | 2026-12-17T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
283 | Electrical Conduiting & Checking |  |  | 2026-12-06T08:00 | 2026-12-07T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
284 | Slab Casting |  |  | 2026-12-08T08:00 | 2026-12-08T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
286 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-12-09T08:00 | 2026-12-09T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
287 | Vertical Reinforcement Work |  |  | 2026-12-09T08:00 | 2026-12-10T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
288 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-12-10T08:00 | 2026-12-13T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
290 | Electrical Conduiting & Checking |  |  | 2026-12-18T08:00 | 2026-12-19T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
274 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-11-16T08:00 | 2026-11-19T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
275 | Slab & Beam Reinforcement Work |  |  | 2026-11-20T08:00 | 2026-11-23T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
276 | Electrical Conduiting & Checking |  |  | 2026-11-24T08:00 | 2026-11-25T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
277 | Slab Casting |  |  | 2026-11-26T08:00 | 2026-11-26T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
279 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-11-27T08:00 | 2026-11-27T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
280 | Vertical Reinforcement Work |  |  | 2026-11-27T08:00 | 2026-11-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
281 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-11-28T08:00 | 2026-12-01T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
282 | Slab & Beam Reinforcement Work |  |  | 2026-12-02T08:00 | 2026-12-05T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
256 | Slab Casting |  |  | 2026-10-08T08:00 | 2026-10-08T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
258 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-10-09T08:00 | 2026-10-09T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
259 | Vertical Reinforcement Work |  |  | 2026-10-10T08:00 | 2026-10-14T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
260 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-10-15T08:00 | 2026-10-18T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
261 | Slab & Beam Reinforcement Work |  |  | 2026-10-19T08:00 | 2026-10-27T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
262 | Electrical Conduiting & Checking |  |  | 2026-10-28T08:00 | 2026-10-29T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
263 | Slab Casting |  |  | 2026-10-30T08:00 | 2026-10-30T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
265 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-10-31T08:00 | 2026-10-31T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
266 | Vertical Reinforcement Work |  |  | 2026-10-31T08:00 | 2026-11-01T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
267 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-11-01T08:00 | 2026-11-04T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
268 | Slab & Beam Reinforcement Work |  |  | 2026-11-05T08:00 | 2026-11-08T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
269 | Electrical Conduiting & Checking |  |  | 2026-11-12T08:00 | 2026-11-13T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
270 | Slab Casting |  |  | 2026-11-14T08:00 | 2026-11-14T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
272 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-11-15T08:00 | 2026-11-15T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
273 | Vertical Reinforcement Work |  |  | 2026-11-15T08:00 | 2026-11-16T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
242 | Slab Casting |  |  | 2026-09-12T08:00 | 2026-09-12T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
331 | Slab & Beam Reinforcement Work |  |  | 2027-03-15T08:00 | 2027-03-18T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
332 | Electrical Conduiting & Checking |  |  | 2027-03-19T08:00 | 2027-03-20T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
333 | Slab Casting |  |  | 2027-03-21T08:00 | 2027-03-21T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
335 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-03-25T08:00 | 2027-03-25T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
336 | Vertical Reinforcement Work |  |  | 2027-03-25T08:00 | 2027-03-26T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
337 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-03-26T08:00 | 2027-03-29T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
338 | Slab & Beam Reinforcement Work |  |  | 2027-03-30T08:00 | 2027-04-02T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
339 | Electrical Conduiting & Checking |  |  | 2027-04-03T08:00 | 2027-04-04T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
340 | Slab Casting |  |  | 2027-04-05T08:00 | 2027-04-05T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
342 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-04-06T08:00 | 2027-04-06T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
343 | Vertical Reinforcement Work |  |  | 2027-04-06T08:00 | 2027-04-07T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
344 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-04-07T08:00 | 2027-04-10T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
345 | Slab & Beam Reinforcement Work |  |  | 2027-04-11T08:00 | 2027-04-14T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
346 | Electrical Conduiting & Checking |  |  | 2027-04-15T08:00 | 2027-04-16T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
373 | Slab & Beam Reinforcement Work |  |  | 2027-06-08T08:00 | 2027-06-11T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
374 | Electrical Conduiting & Checking |  |  | 2027-06-12T08:00 | 2027-06-13T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
375 | Slab Casting |  |  | 2027-06-14T08:00 | 2027-06-14T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
377 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-06-15T08:00 | 2027-06-15T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
293 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2026-12-21T08:00 | 2026-12-21T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
294 | Vertical Reinforcement Work |  |  | 2026-12-22T08:00 | 2026-12-26T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
295 | Shuttering for Column, Wall, Beam & Slab |  |  | 2026-12-27T08:00 | 2026-12-30T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
296 | Slab & Beam Reinforcement Work |  |  | 2026-12-31T08:00 | 2027-01-06T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
297 | Electrical Conduiting & Checking |  |  | 2027-01-07T08:00 | 2027-01-08T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
298 | Slab Casting |  |  | 2027-01-09T08:00 | 2027-01-09T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
300 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-01-10T08:00 | 2027-01-10T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
301 | Vertical Reinforcement Work |  |  | 2027-01-10T08:00 | 2027-01-11T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
302 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-01-11T08:00 | 2027-01-14T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
303 | Slab & Beam Reinforcement Work |  |  | 2027-01-15T08:00 | 2027-01-18T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
304 | Electrical Conduiting & Checking |  |  | 2027-01-19T08:00 | 2027-01-20T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
305 | Slab Casting |  |  | 2027-01-21T08:00 | 2027-01-21T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
307 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-01-22T08:00 | 2027-01-22T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
308 | Vertical Reinforcement Work |  |  | 2027-01-22T08:00 | 2027-01-23T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
309 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-01-23T08:00 | 2027-01-27T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
310 | Slab & Beam Reinforcement Work |  |  | 2027-01-28T08:00 | 2027-01-31T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
311 | Electrical Conduiting & Checking |  |  | 2027-02-01T08:00 | 2027-02-02T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
312 | Slab Casting |  |  | 2027-02-03T08:00 | 2027-02-03T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
314 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-02-04T08:00 | 2027-02-04T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
315 | Vertical Reinforcement Work |  |  | 2027-02-04T08:00 | 2027-02-05T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
316 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-02-05T08:00 | 2027-02-08T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
317 | Slab & Beam Reinforcement Work |  |  | 2027-02-09T08:00 | 2027-02-12T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
318 | Electrical Conduiting & Checking |  |  | 2027-02-13T08:00 | 2027-02-14T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
321 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-02-16T08:00 | 2027-02-16T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
322 | Vertical Reinforcement Work |  |  | 2027-02-17T08:00 | 2027-02-21T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
323 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-02-22T08:00 | 2027-02-25T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
324 | Slab & Beam Reinforcement Work |  |  | 2027-02-26T08:00 | 2027-03-04T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
325 | Electrical Conduiting & Checking |  |  | 2027-03-05T08:00 | 2027-03-06T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
326 | Slab Casting |  |  | 2027-03-07T08:00 | 2027-03-07T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
328 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-03-08T08:00 | 2027-03-08T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
329 | Vertical Reinforcement Work |  |  | 2027-03-08T08:00 | 2027-03-09T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
330 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-03-09T08:00 | 2027-03-14T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
291 | Slab Casting |  |  | 2026-12-20T08:00 | 2026-12-20T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
319 | Slab Casting |  |  | 2027-02-15T08:00 | 2027-02-15T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
347 | Slab Casting |  |  | 2027-04-17T08:00 | 2027-04-17T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
349 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-04-18T08:00 | 2027-04-18T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
350 | Vertical Reinforcement Work |  |  | 2027-04-18T08:00 | 2027-04-19T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
351 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-04-19T08:00 | 2027-04-22T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
352 | Slab & Beam Reinforcement Work |  |  | 2027-04-23T08:00 | 2027-04-26T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
353 | Electrical Conduiting & Checking |  |  | 2027-04-27T08:00 | 2027-04-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
354 | Slab Casting |  |  | 2027-04-29T08:00 | 2027-04-29T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
356 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-04-30T08:00 | 2027-04-30T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
357 | Vertical Reinforcement Work |  |  | 2027-05-02T08:00 | 2027-05-06T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
358 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-05-07T08:00 | 2027-05-10T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
359 | Slab & Beam Reinforcement Work |  |  | 2027-05-11T08:00 | 2027-05-18T20:00 | 100.0 | 77.0h | 0.0h | 77.0h | 0.0 | 0.0h
360 | Electrical Conduiting & Checking |  |  | 2027-05-19T08:00 | 2027-05-20T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
361 | Slab Casting |  |  | 2027-05-21T08:00 | 2027-05-21T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
363 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-05-22T08:00 | 2027-05-22T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
364 | Vertical Reinforcement Work |  |  | 2027-05-22T08:00 | 2027-05-23T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
365 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-05-23T08:00 | 2027-05-26T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
366 | Slab & Beam Reinforcement Work |  |  | 2027-05-27T08:00 | 2027-05-30T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
367 | Electrical Conduiting & Checking |  |  | 2027-05-31T08:00 | 2027-06-01T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
368 | Slab Casting |  |  | 2027-06-02T08:00 | 2027-06-02T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
370 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-06-03T08:00 | 2027-06-03T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
371 | Vertical Reinforcement Work |  |  | 2027-06-03T08:00 | 2027-06-04T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
372 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-06-04T08:00 | 2027-06-07T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
384 | Deshuttering of Vertical, Grid Marking & Bracket Fixing |  |  | 2027-06-27T08:00 | 2027-06-27T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
385 | Vertical Reinforcement Work |  |  | 2027-06-27T08:00 | 2027-06-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
386 | Shuttering for Column, Wall, Beam & Slab |  |  | 2027-06-28T08:00 | 2027-07-01T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
387 | Slab & Beam Reinforcement Work |  |  | 2027-07-02T08:00 | 2027-07-05T20:00 | 100.0 | 44.0h | 0.0h | 44.0h | 0.0 | 0.0h
388 | Electrical Conduiting & Checking |  |  | 2027-07-06T08:00 | 2027-07-07T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
389 | Slab Casting |  |  | 2027-07-08T08:00 | 2027-07-08T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
431 | PCC |  |  | 2025-10-25T08:00 | 2025-10-26T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
430 | Dressing |  |  | 2025-10-19T08:00 | 2025-10-24T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
440 | Dressing |  |  | 2025-10-25T08:00 | 2025-10-26T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
441 | PCC |  |  | 2025-10-27T08:00 | 2025-10-28T20:00 | 100.0 | 22.0h | 0.0h | 22.0h | 0.0 | 0.0h
452 | Lean Wall Concreting - 4.35 m |  |  | 2025-11-01T08:00 | 2025-11-20T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
506 | RW - South NTA - 1st to 2nd Slab |  |  | 2026-01-09T08:00 | 2026-01-29T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
494 | RW- North NTA - FDN to 1st Slab |  |  | 2025-12-23T08:00 | 2026-01-11T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
483 | RW- East NTA - FDN to 1st Slab |  |  | 2025-12-16T08:00 | 2026-01-04T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
472 | RW- South NTA - FDN to 1st Slab |  |  | 2025-12-09T08:00 | 2025-12-28T20:00 | 100.0 | 220.0h | 0.0h | 220.0h | 0.0 | 0.0h
7 | GFC Drawing Receipt |  |  | 2025-10-18T08:00 | 2025-10-18T20:00 | 100.0 | 11.0h | 0.0h | 11.0h | 0.0 | 0.0h
8 | Steel Receipt |  |  | 2025-11-06T08:00 | 2025-11-10T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h
38 | Rock Anchoring 4 Nos - Client Scope |  |  | 2025-10-31T08:00 | 2025-11-04T20:00 | 100.0 | 55.0h | 0.0h | 55.0h | 0.0 | 0.0h